9999999999999999999999999999999999999**zzzzzzzzzzzzzzzzzzzzzzzzzzzzzzz

RATLOU LOCAL MUNICIPALITY

4th quarter report

PERIOD 01 APRIL -30 JUNE 2023

OVERALL PERFORMANCE PER KEY PERFORMANCE AREA

|  | MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | MUNICIPAL FINANCIAL VIABILITY | LOCAL ECONOMIC DEVELOPMENT | INFRASTRUCTURE AND BASIC SERVICES | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | SPATIAL RATIONALE | OVERALL PERFORMANCE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL KPIs PLANNED FOR THE QUARTER | 16 | 13 | 06 | 09 | 24 | 02 | 70 |
| TOTAL ACHIEVED | 09 | 08 | 03 | 05 | 14 | 02 | 41 |
| TOTAL NOT ACHHIEVED | 07 | 05 | 03 | 04 | 10 | 0 | 29 |
| PERFORMANCE ON PERCENTAGES | 56% | 61% | 50% | 55% | 58% | 100% | 58% |

| KPA: MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING & PERFORMANCE MANAGEMENT | Number of Developed/reviewed/amended IDP Adopted | 2022/2027 IDP | 2023/2024 IDP Adopted by 31 May 2023 | Community Consultation & Adopted 23/24 IDP | 1 Community Consultation was conducted and the IDP has been adopted | N/A | N/A |
|  | Budget (r) |  | R 190 000 |  |  |  |  |
|  | Number of Developed & Approved SDBIP | 2017/2022 IDP | Service Delivery and Budget Implementation Plan Approved by 12 June 2023 | Approved 23/24 SDBIP by the Mayor | 1 Service Delivery and Budget Implementation plan was approved by the Mayor | N/A | N/A |
|  | Budget (r) |  | Same As Above |  |  |  |  |
|  | Number of IDP Rep forums held | 2021/2022 SDBIP | 2 IDP Representative forum meetings held (Q3 & 4) | 1 IDP Representative forum meeting held | The target was not achieved | The IDP Representative forum meeting could not be held due to tight schedule of the political office bearer | The schedule of meetings will be addressed in the new financial year |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | 2022/2027 IDP & Budget Schedule Activities adopted by Council | 2017/2022 Schedule of Activities (IDP/Budget) | 1 IDP & Budget Schedule of Activities Adopted by 31 August 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | Number of Mid-term Assessment Held | 2021/2022 Mid-Term | 1 Mid Term Assessment held by 31 January 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING AND PERFORMANCE MANAGEMENT | Number of Strategic sessions held | 2020/2021 | 1 Strategic Planning Session held by 30 September 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 420 000 |  |  |  |  |
|  | Number of Annual Report approved by council | 2021/2022 Annual Report | 2021/22 Annual Report Adopted by Council by 31 May 2023 | 1 Annual Report adopted | The target was not achieved | MPAC did not conduct public participations on Oversight report | The Mayor is expected to intervene on this matter |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | PMS Policy developed & adopted | 2016/2017 PMS policy | 1 PMS Policy developed & adopted by Council by 31 May 2023 | Adopted PMS Policy | The target was not achieved | Consultation on reviewed policies to be adopted is not yet finalized due to unavailability of other stakeholders inputs .eg DECOG, COGTA and SALGA | Letters for inputs solicitation have been issued and we are awaiting their responses in that regard |
|  | Budget (R) |  | Operational |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE TECHNOLOGY EFFICIENCY | Number of IT Master Plans Developed & adopted | 2019/2020 | 1 IT Master Plans Developed & adopted by Council by 30 June 2023 | 1 IT Master Plans Developed | The target was not achieved | The target was not achieved due lack of capacity within IT unit as the post of a Manager ICT has since been vacant | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (r) |  | R 150 000 |  |  |  |  |
|  | Number of Reports on Updated Municipal Website | 2021/2022 SDBIP | 2 Reports on Updated Municipal Website (1 Per quarter) | 1 Report on Updated Municipal Website | 1 Report on Updated Municipal Website was compiled | N/A | N/A |
|  | Budget (r) |  | R100 000 |  |  |  |  |
|  | Number of reports on IT, Telephones complains received and submitted to Council for noting | Existing | 2 Reports on IT, Telephones complains received and submitted to Council for noting. (1 Per quarter) | 1 Report on IT, Telephones complains received and submitted to Council for noting | 1 Report on IT, Telephones complains received was submitted to Council for noting | N/A | N/A |
|  | Budget (r) |  | R 2 650 000 |  |  |  |  |
|  | Number of Reports on Software and Hardware updated | Existing | 2 Reports on Software & Hardware updates (1 Per quarter) | 1 Report on Software & Hardware updates | 1 Report on Software & Hardware updates was compiled | N/A | N/A |
|  | Budget (r) |  | R 199 205 |  |  |  |  |
|  | Number of Operational Disaster and Business Continuity Plans Reviewed | Existing | 1 Operational Disaster and Business Continuity Plans Reviewed by 31 May 2023 | 1 Operational Disaster and Business Continuity Plans Reviewed | The target was not achieved | The target was not achieved due lack of capacity within IT unit as the post of a Manager ICT has since been vacant | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (r) |  | R 350 000l |  |  |  |  |

| KPA: MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| RETAIN & RECRUIT TALENTED EMPLOYEES | Number of Revised Policies adopted by Council | 6 Policies | 24 HR Policies reviewed & adopted. 30 June 2023 | 24 HR Policies Adopted | 24 Human Resource Management policies were reviewed and adopted | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
|  | Number of Human Resource Development Strategy Developed & Reviewed | Existing | 1 Human Resource Development Strategy Developed & Reviewed by 30 June 2023 | 1 Human Resource Development Strategy Developed & Reviewed | 1 Human Resource Development Strategy was developed & reviewed | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
| PROMOTE INNOVATION LEARNING AND GROWTH | Number of 2022/2023 Workplace Skills Development Plan (WSDP) Developed & submitted to LGSETA | 2021/2022 WSDP | 1 WSDP submitted to LGSETA by 30 April 2023 | WSDP Submitted to LGSETA | Workplace Skills Development Plan (WSDP) Developed & Submitted to LGSETA on 30 April 2023 | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
|  | Number of applicants benefiting from the bursary fund | 6 Bursars | 10 Bursars benefiting from the Bursary fund by 30 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget ® |  | R 400 000 |  |  |  |  |
|  | Number of Workplace Skills Development Plan targets achieved | New | 15 Workplace Skills Development Plan targets achieved. By 30 June 2023 | 4 Workplace Skills Development Plan targets achieved | The target was not achieved | The delay was caused by nonresponsive of service providers | Accredited service Providers were appointed to facilitate the planned trainings within the first quarter of the new financial year. |
|  | Budget ® |  | R 630 000 |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| ACHIEVE EMPLOYMENT EQUITY | Number Employment Equity Plan Developed & submitted to the dept of labour | Employment Equity Plan 2021/2022 | 1 EEP completed and submitted by 15 January 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
|  | Number of Employment Equity targets achieved | 2 Employment equity Targets | 2 EEP Targets achieved by 30 June 2023 | 2 EEP Targets achieved by 30 June 2023 | The target was not achieved | Consultation on reviewed organizational structure to be adopted is not yet finalized due to unavailability of other stakeholder’s inputs .eg DECOG, COGTA and SALGA | Letters for inputs solicitation have been issued and we are awaiting their responses in that regard |
|  | Budget ® |  | Operational |  |  |  |  |
| ACHIEVE POSITIVE EMPLOYEE CLIMATE | Number of LLF Meetings held | 3 LLF meeting | 6 LLF Meetings held by 30 June 2023 | 1 LLF Meeting held | 1 LLF Meetings was held by 13 April 2023 | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of employees that have signed Code of conduct | 212 employees | 230 employees that have signed Code of conduct by 30 June 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Promote Financial Accountability | 2023/2024 Budget approved by Council | 2022/2023 Budget | 2023/2024 Budget approved by 31 May 2023 | Approved Budget by 31 May 2023 | 2023/24 Budget was approved by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Budget Related policies* adopted by Council | 13 Policies | 16 Policies Adopted by 31 May 2023 | 16 Policies Adopted by Council | 16 Policies were Adopted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | 2022/2023 Adjustment Budget Approved by Council | 2022122 Adjustment budget approved | 2022/2023 Adjustment Budget Approved by 28 February 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Council approved 2022/203 Annual Financial Statements (AFS) submitted to the Office of the Auditor-General (A-G) | 2020/2021 Audited AFS | AFS submitted to A-G by 30 August 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R1 900 000 |  |  |  |  |
|  | Number of Supply Chain Management reports submitted to council | Existing | 4 Supply Chain Management reports submitted to council for noting. (1 Per quarter) | 1 Supply Chain Management report submitted to Council for noting. | 1 Supply Chain Management report was submitted to Council for noting. | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Credit Control Policy Reviewed | Policy Existing | 1 Credit control Policy reviewed by 31 May 2023 | 1 Credit control Policy reviewed | 1 Credit control Policy was reviewed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number Credit control implemented | Policy Existing | 1 Credit control implemented by 30 September 22 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number Indigent Policies Reviewed | Policy Existing | 1 Indigent Policy Reviewed by 31 May 2023 | 1 Indigent Policy Reviewed | 1 Indigent Policy was reviewed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Indigent Policies implemented | Policy Existing | 1 Indigent Policies implemented by 30 September 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Consumer Awareness campaigns held | New | 2 Consumer Awareness campaigns held by 30 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of MPRA meetings held | Existing | 3 MPRA meetings held (1 Per quarter) | 1 MPRA meetings held | The target was not achieved | The MPRA Meeting was not held due to unprocessed last step of Accounts Spreadsheets of Farmers disputes. | The Municipality to address the Service Provider payment issue for finalisation of the dispute Accounts Spread Sheets. |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | % Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 95% | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 95% Collection of billed revenue | Rent & Electricity = 68,45 % Rates & Taxes 14,22 % Licencing Commission = 78,64 % Average = 53,77% | Account spread sheets for Disputes Accounts not yet processed. | The municipality met with Farmers Union Representative to give proposal and final advise to close the dispute by granting discount for 10 years ( From 2009/10 to 2018/19) be written off and the remaining 4 Years ( From 2019/20 to 2022/23) be paid in order close the dispute lodged. However the Farmers Union Rep did not agree on the proposal made and demand to pay only 2 years. |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Achieve Clean Audit | Number of quarterly AFS submitted to Council | New | 4 quarterly AFS submitted to Council for noting (1 per quarter) | 1 quarterly AFS submitted to Council for noting | 0 quarterly AFS submitted to Council for noting | The Service Provider who was previously appointed for Caseware did not share the AFS report | It has been resolved that the new service provider SLA must have a clause that says a caseware file should be submitted with every invoice |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Audit Plans Developed to address Auditor – General (A-G Queries adopted by Council | 2021/22 Audit Action Plan | 1 Audit Action Plan Developed by 31 January 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on the Implementation of the Audit Action Plan noted by Council | Existing | 2 Reports on the Implementation of the Audit Action Plan noted by Council 3rd and 4th Quarter | 1 Report on the Implementation of the Audit Action Plan noted by Council. 3rd and 4th Quarter | 1 Report on the implementation of Audit Action Plan has been submitted and adopted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of PAAP reports included in the Management Meeting | PAAP Progress Report | 2 PAAP reports included in the Management Meeting (1 per quarter) | 1 PAAP reports included in the Management Meeting | 1 PAAP report was included in the Management Meeting | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Improve Assets Management | Number of Asset registers updated | Existing | 1 Asset registers updated. 30 September 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of reports on assets verification noted by Council | Existing | 4 reports on assets verification noted by Council (1 per quarter) | 1 Report on assets verification noted by Council | 1 Report on assets verification was noted by Council. | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Asset committee established | Existing | 1 Asset committee established by 30 June 2023 | 1 Asset committee established | The target was not achieved | The committee was not established due to change of Acting Senior Managers | The committee will be established in the first quarter of the new financial year |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of meetings held of the asset committee | Existing | 1 Asset Committee meeting by 30 June 2023 | 1 Asset Committee meeting held | The target was not achieved | The committee was not established due to change of Acting Senior Managers | The committee will be established in the first quarter of the new financial year |
|  | Budget (R) |  | Operational |  |  |  |  |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Jobs created through Expanded Public Works Programme, Community Workers Programme, Capital Projects and other Local Economic Development initiatives | 1000 Jobs | 1000 Jobs created 30 June 2023 | 1000 Jobs created | 1164 jobs were created | The department has subsequent to the initial allocation of 1000 recruitment, granted a permission for additional recruits | N/A |
|  | Budget (R) |  | R31 497 250 (MIG) |  |  |  |  |
|  |  |  | R1 239 000 EPWP |  |  |  |  |
|  | Number of Billboards erected | Information Boards | - Billboards erected in Ratlou South & North by 30 March 2023 | 2 Billboards erected | The target was not achieved | Due to ack of LED Manager to oversee the KPI LED to non-performance | The target will be addressed in the first quarter of the new financial year |
|  | Budget (R) |  | R 70 000 |  |  |  |  |
|  | Number of LED & Tourism Strategies Developed & Adopted | 2012-2017 strategy | 1 LED Strategy Developed & Adopted by Council by 30 June 2023 | Final LED Strategy | The target was not achieved | There was a delay in the appointment of the Service Provider | Once completed it will be adopted in the new financial year |
|  | Budget (R) |  | R 1 230 000 |  |  |  |  |
|  | Number of SMMEs/Cooperatives support initiatives | 4 Support initiatives | 6 Support initiatives by 30 June 2023 ( Funding, Business Plan Development, exhibitions, Training & Workshops) | 2 Support initiative | 2 Support initiatives were achieved | N/A | N/A |
|  | Budget (R) |  | R500 000 |  |  |  |  |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of reports on the implementation of the SLP | Existing | 2 reports on the implementation of the SLP (1 per quarter) | 1 report on the implementation of the SLP | 1 report on the implementation of the SLP was compiled | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Signage & Branding Erected (Information Boards) | 10 Signage & Branding | 10 Signage & Branding Erected by (Information Boards)30 June 2023 | 10 Signage & Branding Erected | The target was not achieved | Due to lack of LED Manager to oversee the KPI led to non-performance | This is planned for the next financial year |
|  | Budget (R) |  | R60 000 |  |  |  |  |
|  | Number of funding applications submitted for the establishment of an Abattoir | New | 1 funding applications submitted for the establishment of an Abattoir by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Heritage, Culture, Arts and Sports events held | New | 2 Heritage, Culture, Arts and Sports events held 30 March 2023 (Q1 & Q 3) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Reports on Eskom Electrification Programme & Projects submitted to Council | Existing | 4 reports on Eskom Electrification Programme & Projects submitted to Council (1 per quarter)) | 1 Report on Eskom Electrification Programme & Projects | 1 Report on Eskom Electrification Programme & Projects was submitted to Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of planned & Emergency Maintenance projects undertaken on municipal facilities | 2 Maintenance Projects | 1 Maintenance Projects done by the 30 June 2023 | 1 Maintenance Projects done | The target was not achieved | Appointment of contractors still outstanding. | Tender re-advertised closing 06 June 2023 |
|  | Budget (R) |  | R2 200 000 |  |  |  |  |
|  | Number of Indigent Household (HH) receiving Free Basic Electricity | 7 500 HH | 7 500 Free Basic Electricity collections per individual household by 30 June 2023 | 7 500 Free Basic Electricity collections per individual household | 8 670 Free Basic Electricity collections per individual household were made | The over performance is due to the increased number of configured Household | N/A |
|  | Budget (R) |  | R 7 000 000 |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Reports on the implementation of Water Projects by DWA&S, NMMDM & Sedibeng noted by Council | Existing | 4 Water Projects Reports noted by Council (1 per quarter) | 1 Water Project Report | 1 Water project report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on Waste Removal noted by Council | Existing | 4 Waste Removal Reports noted by Council (1 per quarter) | 1 Waste removal Report | 1 Waste Removal Report was noted by Council | N/A | N/A |
|  | Budget (R) |  | R2 200 000 |  |  |  |  |
|  | Number of Reports on Housing Projects Implemented by DHS noted by Council | Existing | 4 Housing Reports noted by Council (1 per quarter) | 1 Housing Report | 1 Housing report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Cemeteries Fenced and provided with VIP Toilet | 18 cemeteries fenced | 1 Cemeteries fenced and provided with VIP Toilets (Lokaleng ) | Project Complete and handed over | The target was not achieved | 1st cemetery complete; 2nd on 80% completion due to late appointment of contractors | Internal Consequence Management Processes implemented |
|  | Budget (R) |  | R 1 900 000 |  |  |  |  |
|  | Number rehabilitated Existing Sports Complex | 2 Sports Complex | 1 Rehabilitated Existing Sports Complex Constructed and Completed (Soccer pitch earthworks complete) by 30 June 2023 (Mareetsane Village) | Project Complete and handed over | The target was not achieved | Site Establishment Completed due to late appointment of contractors | Internal Consequence Management Processes implemented |
|  | Budget( R) |  | R 7 172 550 |  |  |  |  |
|  | Number of Roads & Storm water constructed | 25km of road paved | 1km Roads & Storm water constructed & completed by 30 June 2023(Setlhwatlhwe and Ramabesa Phase 02) | Project Complete and handed over | The target was not achieved | Due to late Appointment of contractors | Internal Consequence Management Processes implemented |
|  | Budget( R) |  | R 16 866 652. 56 |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of Audit Charter Plan developed & reviewed | 1 | Audit Charter & Plan developed by 31 December 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Audit Committee sittings held | 4 | 4 Audit Committee sittings held. (1 per quarter) | 1 Audit Committee sittings | 2 Audit Committee sittings were held 12 June 2023 & 26 June 2023 | The over performance was a result of additional meeting of the Committee with AMM | In-committee meetings to form part of ordinary meetings whereby in-committee will start prior normal meetings. |
|  | Budget (R) |  | R200 000 |  |  |  |  |
|  | Number of Internal Audits Conducted | 4 Internal Audit | 4 Internal Audits Conducted | 1 Internal Audits Conducted | 1 Internal Audit has been conducted | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | Number of Internal Audit (IA) Plan Adopted by Audit Committee | 1 | 1 IA Plan developed. by 31 May 2023 | 1 IAP Approved by 31 May 2023 | 1 IAP has been approved by the Committee | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | Number of Risk Management policy (RMP) Reviewed and adopted | Policy Existing | 1 Reviewed RMP by 31 May 2023 | 1 RMP Approved by 31 May 2023 | The target was not achieved | Due to unavailability of a dedicated official and Risk Management Committee within the Municipality | The management with the assistance of the Audit Committee has resolved to establish the Risk Management Committee and also to |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of Internal Audit Reports Submitted to Audit Committee for Consideration | 4 | 4 Internal Audit Reports submitted to Audit Committee for consideration. ( 1 per quarter) | 1 Internal Audit Report submitted | 1 Internal Audit Report submitted | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of revised Risk Management Strategy (RMS) approved by Council | Strategy in Place | 1 Revised RMS by 31 May 2023 | 1 RMS Revised & Adopted Strategy | The target was not achieved | The Municipality does not a functional Risk Management Unit | Ratlou Local Municipality and Audit Committee had resolved to resuscitate the establishment of Risk Management committee and it is expected to be fully functional in the new financial year |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Revised Fraud and Corruption Strategy adopted by Council | Strategy in Place | 1 Revised Fraud & Corruption Strategy Adopted by Council by 30 June 2023 | 1 Fraud & Corruption Strategy Revised & adopted | The target was not achieved | The Municipality does not a functional Risk Management Unit | Ratlou Local Municipality and Audit Committee had resolved to resuscitate the establishment of Risk Management committee and it is expected to be fully functional in the new financial year |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of MPAC Reports submitted to Council for noting | 4 | 4 MPAC Reports submitted to council for noting. (1 per quarter) | 1 MPAC Report submitted to Council | The target was not achieved | MPAC report was not submitted as there was no MPAC sitting held owing to the quorum | The Office of the Speaker to intervene in the matter |
|  | Budget (R) |  | R50 000 |  |  |  |  |
|  | Number of Support Training Conducted for MPAC & Rules Committee(Training on Roles & Responsibility) | 2 | 2 Support Training Conducted for MPAC & Rules Committee (Q2 & Q4 | 1 Support Training Conducted | The target was not achieved | Rules Committee training was arranged for27 June 2023 and was postponed due to urgent COGTA visit | The Support training has been rescheduled to August 2023 |
|  | Budget (R) |  | Same As Above |  |  |  |  |
| PROMOTE COMMUNITY PARTICIPATION | Number of Ward Committees Functional | 14 Ward Committees | 14 Functional Ward Committees | 14 Functional Ward Committees | 14 Ward Committees are functional | N/A | N/A |
|  | Budget (R) |  | R2 604 000 |  |  |  |  |
|  | Number of Ward Committee reports noted by Council | Existing | 4 Reports on Ward Committees noted by Council | 1 Report on Ward Committees | 1 report on Ward committees was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Ward Committees supplied with Stationery | 140 Ward Committees | 140 Ward Committees supplied with Stationery by 30 June 2023 | 140 Ward Committees supplied with Stationery | The target was not achieved | The target could not be achieved due to insufficient budget, and this was only realized when the procurement process has already been committed | The SCM has agreed to start with the procurement in the first quarter of the new financial year |
|  | Budget (R) |  | R100 000 |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Performance Indicator | Baseline | Revised Annual Target | Quarter 4 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE COMMUNITY PARTICIPATION | Number of Public Participation Events Supported | 4 events | 12 (3 x IDP/Budget/PMS, 3 x Annual Report, 2 x Imbizos & 4 x Ward Comm. Functions) | 3 x (IDP/Budget/ PMS) 1 x Ward Committed Function | The target was not achieved. | 6 Public Participation events were supported as MPAC did not conduct their Public Participation events | N/A |
|  | Budget (R) |  | R100 000 |  |  |  |  |
|  | Number of Support Initiatives for Traditional Leaders Implemented | 4 Support Initiatives | 4 Support Initiatives for Traditional Leaders Implemented (1 per qurter) | 1 Support Initiative | 1 support initiative has been achieved | N/A | N/A |
|  | Budget (R) (R) |  | R 352 000 |  |  |  |  |
|  | Number of Dipitso tsa Baagi Held | 2 Diitso tsa Baagi | 2 Dipitso tsa Baagi Held (Q3 & Q4) | 1 Dipitso tsa Baagi Held | The target was not Achieved | Due to tight schedule of the political office bearer | The meetings will be arranged for the new financial year |
|  | Budget (R) |  | R50 000 |  |  |  |  |
|  | Number of Youth Summit Held | 1 Youth Summit | 1 Youth Summit Held by 30 June 2023 | 1 Youth Summit held | 1 Youth Summit was held | N/A | N/A |
|  | Budget (R) |  | R200 000 |  |  |  |  |
|  | Number of Youth Career Exhibition Held | 1 Youth Career Exhibition | 1 Youth Career Exhibition Held by 30 June 2023 | 1 Youth Career Exhibition held | 1 Youth Career Exhibition was held | N/A | N/A |
|  | Budget (R) |  | As indicated above |  |  |  |  |
|  | Number of Youth Development Programmes Held | 4 Youth Development programmes | 4 Youth Development programmes held (1 per quarter) | 1 Youth Development programme held | 1 Youth Development programme was held | N/A | N/A |
|  | Budget (R) |  | As indicated above |  |  |  |  |
|  | Number of Disability Forum Meetings Held | 4 Disability Forum | 1 Disability Forum Meeting Held by 30 June 2023 | 1 Disability Forum Meetings Held | 1 Disability forum meeting was held | N/A | N/A |
|  | Budget (R) |  | R 50 000 |  |  |  |  |

KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION. Objectives; Performance Indicator; Baseline; Revised Annual Target; Quarter 4 Target; Actual Performance; Reasons for variance (under / over performance); Corrective measures. ENHANCE COMMUNICATION; Number of Communication strategy reviewed and adopted by council; Strategy in Place; 1 Communication Strategy Reviewed and adopted by 31 May 2022; 1 Reviewed & Adopted Strategy; The target was not achieved; Communication strategies were not adopted because its part of the policy that we supposed to be adopted by council; The strategy will be reviewed in the next financial year. Budget (R) (R); Operational. Number of Reports on Operational Tele Centres; 1; 3 Operational Tele Centres( Tshidilamolo, Kraaipan, Setlagole); 1 Operational Tele Centre; 1 Telecentre is operational; N/A; N/A. Budget (R) (R); R5700 000. Number of Reports on Moderate and Assessment; 1; 1 Moderate & Assessment noted by Council; 1 Report noted; 1 Report has been noted by Council; N/A; N/A. Budget (R); Same As Above. Number of Graduation Ceremonies held; 1 Graduation ceremony; 1 Graduation Ceremonies held by 30 June 2023; 1 Graduation Ceremonies held; The Target was not achieved; The Municipality is awaiting the quality assurance report from SETA before the Graduation Ceremony could take place; Continuous follow-ups are being made. Budget (R); Same As Above. Number of Accredited Tele centres; 1; 1 Tele Centre Accredited by 30 June 2022; 1 Telecentre Accredited; 1 Telecentre has been accredited; N/A; N/A. Budget (R); Same As Above. SPATIAL RATIONALE. Objectives; Performance Indicator; Baseline; Revised Annual Target; Quarter 4 Target; Actual Performance; Reasons for variance (under / over performance); Corrective measures. IMPROVE SPATIAL PLANNING; Number of General Valuation Rolls implemented; 2012/2017 SDF; 1 General Valuation Roll implemented by 30 June 2023; Lodging of Objections; The target was achieved; N/A; N/A. Budget (R); R1 320 000. Number of Municipal Planning Tribunal appointed; New; 1 MPT appointed by 30 June 2023; MPT appointed; The target was achieved; N/A; N/A. Budget (R); Operational.