9999999999999999999999999999999999999**zzzzzzzzzzzzzzzzzzzzzzzzzzzzzzz

RATLOU LOCAL MUNICIPALITY

ANNUAL report

PERIOD 01 JULY 2022 – 30 JUNE 2023

OVERALL PERFORMANCE PER KEY PERFORMANCE AREA

|  | MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | MUNICIPAL FINANCIAL VIABILITY | LOCAL ECONOMIC DEVELOPMENT | INFRASTRUCTURE AND BASIC SERVICES | GOOD GOVERNANCE | SPATIAL RATIONALE | OVERALL PERFORMANCE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL KPIs PLANNED FOR THE QUARTER | 22 | 20 | 08 | 09 | 25 | 02 | 86 |
| TOTAL ACHIEVED | 10 | 13 | 02 | 05 | 14 | 02 | 46 |
| TOTAL NOT ACHHIEVED | 12 | 07 | 06 | 04 | 11 | 0 | 40 |
| PERFORMANCE ON PERCENTAGES | 45% | 65% | 25% | 55% | 56% | 100% | 53.% |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING & PERFORMANCE MANAGEMENT | Number of Developed/reviewed/amended IDP Adopted | 2022/2027 IDP | 2023/2024 IDP Adopted by 31 May 2023 | 1 Community Consultation was conducted and the IDP has been adopted | N/A | N/A |
|  | Budget (r) |  | R 190 000 |  |  |  |
|  | Number of Developed & Approved SDBIP | 2017/2022 IDP | Service Delivery and Budget Implementation Plan Approved by 12 June 2023 | 1 Service Delivery and Budget Implementation plan was approved by the Mayor | N/A | N/A |
|  | Budget (r) |  | Same As Above |  |  |  |
|  | Number of IDP Rep forums held | 2021/2022 SDBIP | 2 IDP Representative forum meetings held (Q 3& 4) | The target was not achieved | The IDP Representative forum meeting could not be held due to tight schedule of the political office bearer | The schedule of meetings will be addressed in the new financial year |
|  | Budget (r) |  | Operational |  |  |  |
|  | 2022/2027 IDP & Budget Schedule Activities adopted by Council | 2017/2022 Schedule of Activities (IDP/Budget) | 1 IDP & Budget Schedule of Activities Adopted by 31 August 2022 | 1 IDP & Budget Schedule of activities has been adopted by Council on the 30 August 2022 | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |
|  | Number of Mid-term Assessment Held | 2021/2022 Mid-Term | 1 Mid Term Assessment held by 31 January 2023 | 1 Mid-Term assessment was successfully conducted by 31 January 2023 | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING AND PERFORMANCE MANAGEMENT | Number of Strategic sessions held | 2020/2021 | 1 Strategic Planning Session held by 30 September 2022 | The strategic planning session was successfully held | N/A | N/A |
|  | Budget (R) |  | R 420 000 |  |  |  |
|  | Number of Annual Report approved by council | 2021/2022 Annual Report | 21/22 Annual Report Adopted by Council by 31 May 2023 | The target was not achieved | MPAC did not conduct public participations on Oversight of the Annual Report | The Mayor is expected to intervene on this matter |
|  | Budget (R) |  | Operational |  |  |  |
|  | PMS Policy developed & adopted | 2016/2017 PMS policy | 1 PMS Policy developed & adopted by Council by 31 May 2023 | The target was not achieved | Consultation on reviewed policies to be adopted is not yet finalized due to unavailability of other stakeholders inputs .eg DECOG, COGTA and SALGA | Letters for inputs solicitation have been issued and we are awaiting their responses in that regard |
|  | Budget (R) |  | Operational |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE TECHNOLOGY EFFICIENCY | Number of IT Master Plans Developed & adopted | 2019/2020 | 1 IT Master Plans Developed & adopted by Council by 30 June 2023 | The target was not achieved | The target was not achieved due lack of capacity within IT unit as the post of a Manager ICT has since been vacant | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (r) |  | R 150 000 |  |  |  |
|  | Number of Reports on Updated Municipal Website | 2021/2022 SDBIP | 2 Reports on Updated Municipal Website (1 Per quarter) | The target was not achieved | 1 report was submitted due lack of internal capacity within the unit | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (r) |  | R100 000 |  |  |  |
|  | Number of reports on IT, Telephones complains received and submitted to Council for noting | Existing | 2 Reports on IT, Telephones complains received and submitted to Council for noting. (1 Per quarter) | The target was not achieved | 1 report was submitted due lack of internal capacity within the unit | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (R) |  | R 2 650 000 |  |  |  |
|  | Number of Reports on Software and Hardware updated | Existing | 2 Reports on Software & Hardware updates (1 Per quarter) | The target was not achieved | 1 report was submitted due lack of internal capacity within the unit | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (R) |  | R 199 205 |  |  |  |
|  | Number of Operational Disaster and Business Continuity Plans Reviewed | Existing | 1 Operational Disaster and Business Continuity Plans Reviewed by 31 May 2023 | The target was not achieved | The target was not achieved due lack of capacity within IT unit as the post of a Manager ICT has since been vacant | The Management has temporarily appointed a dedicated Official whilst the recruitment of a substantive official is underway |
|  | Budget (R) |  | R 350 000l |  |  |  |

| KPA: MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| RETAIN & RECRUIT TALENTED EMPLOYEES | Number of Revised Policies adopted by Council | 6 Policies | 24 HR Policies reviewed & adopted. 30 June 2023 | 24 Human Resource Management policies were reviewed and adopted | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |
|  | Number of Human Resource Development Strategy Developed & Reviewed | Existing | 1 Human Resource Development Strategy Developed & Reviewed by 30 June 2023 | 1 Human Resource Development Strategy was developed & reviewed | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |
| PROMOTE INNOVATION LEARNING AND GROWTH | Number of 2022/2023 Workplace Skills Development Plan (WSDP) Developed & submitted to LGSETA | 2021/2022 WSDP | 1 WSDP submitted to LGSETA by 30 April 2023 | Workplace Skills Development Plan (WSDP) Developed & Submitted to LGSETA on 30 April 2023 | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |
|  | Number of applicants benefiting from the bursary fund | 6 Bursars | 10 Bursars benefiting from the Bursary fund by 30 March 2023 | The target was not achieved | The policy regulating the allocation of Bursaries is not yet reviewed | The policy will be reviewed during the last quarter of the current financial year. |
|  | Budget ® |  | R 400 000 |  |  |  |
|  | Number of Workplace Skills Development Plan targets achieved | New | 15 Workplace Skills Development Plan targets achieved. By 30 June 2023 | The target was not achieved | The delay was caused by nonresponsive of service providers | Accredited service Providers were appointed to facilitate the planned trainings within the first quarter of the new financial year. |
|  | Budget ® |  | R 630 000 |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| ACHIEVE EMPLOYMENT EQUITY | Number Employment Equity Plan Developed & submitted to the dept of labour | Employment Equity Plan 2021/2022 | 1 EEP completed and submitted by 15 January 2023 | The Employment Equity Plan was submitted on 12 January 2023 | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |
|  | Number of Employment Equity targets achieved | 2 Employment equity Targets | 2 EEP Targets achieved by 30 June 2023 | The target was not achieved | Consultation on reviewed organizational structure to be adopted is not yet finalized due to unavailability of other stakeholder’s inputs .eg DECOG, COGTA and SALGA | Letters for inputs solicitation have been issued and we are awaiting their responses in that regard |
|  | Budget ® |  | Operational |  |  |  |
| ACHIEVE POSITIVE EMPLOYEE CLIMATE | Number of LLF Meetings held | 3 LLF meeting | 6 LLF Meetings held by 30 June 2023 | The target was not achieved | 2 LLF meetings were held due to unavailability and commitments of the Accounting Officer during the reporting period | LLF meetings will be held in quarter two |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of employees that have signed Code of conduct | 212 employees | 230 employees that have signed Code of conduct by 31 July 2022 | 230 employees have signed Code of conduct | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Promote Financial Accountability | 2023/2024 Budget approved by Council | 2022/2023 Budget | 2023/2024 Budget approved by 31 May 2023 | 2023/24 Budget was approved was by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Budget Related policies* adopted by Council | 13 Policies | 16 Policies Adopted by 31 May 2023 | 16 Policies were Adopted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | 2022/2023 Adjustment Budget Approved by Council | 2022122 Adjustment budget approved | 2022/2023 Adjustment Budget Approved by 28 February 2023 | 2022/2023 Adjustment budget approved on 28 February 2023 | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Council approved 2022/203 Annual Financial Statements (AFS) submitted to the Office of the Auditor-General (A-G) | 2020/2021 Audited AFS | AFS submitted to A-G by 30 August 2022 | The Annual Financial Statement were submitted to Auditor-General on 31 August 2022 | N/A | N/A |
|  | Budget (R) |  | R1 900 000 |  |  |  |
|  | Number of Supply Chain Management reports submitted to council | Existing | 4 Supply Chain Management reports submitted to council for noting. (1 Per quarter) | 4 Supply Chain Management reports were submitted to council for noting | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Credit Control Policy Reviewed | Policy Existing | 1 Credit control Policy reviewed by 31 May 2023 | 1 Credit control Policy was reviewed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number Credit control implemented | Policy Existing | 1 Credit control implemented by 30 September 22 | 1 Credit control has been implemented | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number Indigent Policies Reviewed | Policy Existing | 1 Indigent Policy Reviewed by 31 May 2023 | 1 Indigent Policy was reviewed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Indigent Policies implemented | Policy Existing | 1 Indigent Policies implemented by 30 September 2022 | 1 Indigent policy has been implemented | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Consumer Awareness campaigns held | New | 2 Consumer Awareness campaigns held by 30 March 2023 | The target was not achieved | The Awareness Campaign that was scheduled for the 28 March 2023 was not held due to commitments that could not be avoided | The awareness has been re-scheduled to the 16th May 2023 |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of MPRA meetings held | Existing | 3 MPRA meetings held (1 Per quarter) | The target was not achieved. | The MPRA Meeting was not held due to unprocessed last step of Accounts Spreadsheets of Farmers disputes. | The Municipality to address the Service Provider payment issue for finalisation of the dispute Accounts Spread Sheets. |
|  | Budget (R) |  | Operational |  |  |  |
|  | % Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 95% | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | Rent & Electricity = 57.25% Rates & Taxes 52.23% Licencing Commission = 62.81% Average = 57.43 % | Account spread sheets for Disputes Accounts not yet processed. | The municipality met with Farmers Union Representative to give proposal and final advise to close the dispute by granting discount for 10 years ( From 2009/10 to 2018/19) be written off and the remaining 4 Years ( From 2019/20 to 2022/23) be paid in order close the dispute lodged. However the Farmers Union Rep did not agree on the proposal made and demand to pay only 2 years. |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| ACHIEVE CLEAN AUDIT | Number of quarterly AFS submitted to Council | New | 4 quarterly AFS submitted to Council for noting (1 per quarter) | The target was not achieved | 2 Quarterly AFS were submitted to Council, The Service Provider who was previously appointed for Caseware did not share the AFS report | It has been resolved that the new service provider SLA must have a clause that says a caseware file should be submitted with every invoice |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Audit Plans Developed to address Auditor – General (A-G Queries adopted by Council | 2021/22 Audit Action Plan | 1 Audit Action Plan Developed by 31 January 2023 | 1 Audit Action Plan has been developed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Reports on the Implementation of the Audit Action Plan noted by Council | Existing | 2 Reports on the Implementation of the Audit Action Plan noted by Council 3rd and 4th Quarter | 2 Reports on the implementation of Audit Action Plan has been submitted and adopted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of PAAP reports included in the Management Meeting | PAAP Progress Report | 2 PAAP reports included in the Management Meeting (1 per quarter) | The target was not achieved | 1 PAAP report was included due to internal Management not holding their meeting as required | The feed on PAAP has been arranged to be accessed online to improve progress |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE ASSETS MANAGEMENT | Number of Asset registers updated | Existing | 1 Asset registers updated. 30 September 2022 | 1 Asset register was updated | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of reports on assets verification noted by Council | Existing | 4 reports on assets verification noted by Council (1 per quarter) | 4 reports on assets verification were noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Asset committee established | Existing | 1 Asset committee established by 30 June 2023 | 0 Asset committee was established | The Assets unit was awaiting the Accounting Officer to finalize the appointment of Committee members | The committee will be established on the first quarter |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of meetings held of the asset committee | Existing | 1 Asset Committee meeting by 30 June 2023 | The target was not achieved | The Assets unit was awaiting the Accounting Officer to finalize the appointment of Committee members | The meeting will be held once the committee has been established in the first quarter |
|  | Budget (R) |  | Operational |  |  |  |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Jobs created through Expanded Public Works Programme, Community Workers Programme, Capital Projects and other Local Economic Development initiatives | 1000 Jobs | 1000 Jobs created 30 June 2023 | 1164 jobs were created | The department has subsequent to the initial allocation of 1000 recruitment granted a permission for additional recruits | N/A |
|  | Budget (R) |  | R31 497 250 (MIG) |  |  |  |
|  |  |  | R1 239 000 EPWP |  |  |  |
|  | Number of Billboards erected | Information Boards | - Billboards erected in Ratlou South & North by 30 March 2023 | The target was not achieved | Due to ack of LED Manager to oversee the KPI LED to non-performance | The Issue of Manager LED will be resolved in the first quarter of the new financial year |
|  | Budget (R) |  | R 70 000 |  |  |  |
|  | Number of LED & Tourism Strategies Developed & Adopted | 2012-2017 strategy | 1 LED Strategy Developed & Adopted by Council by 30 June 2023 | The target was not achieved | There was a delay in the appointment of the Service Provider | Once completed it will be adopted in the new financial year |
|  | Budget (R) |  | R 1 230 000 |  |  |  |
|  | Number of SMMEs/Cooperatives support initiatives | 4 Support initiatives | 6 Support initiatives by 30 June 2023 ( Funding, Business Plan Development, exhibitions, Training & Workshops) | The target was not achieved | 2 Support initiatives were achieved due to ack of LED Manager to oversee the KPI LED to non-performance | The Issue of Manager LED will be resolved in the first quarter of the new financial year |
|  | Budget (R) |  | R500 000 |  |  |  |
|  | Number of reports on the implementation of the SLP | Existing | 2 reports on the implementation of the SLP (1 per quarter) | 2 reports on the implementation of the SLP wee submitted | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Signage & Branding Erected (Information Boards) | 10 Signage & Branding | 10 Signage & Branding Erected by (Information Boards)30 June 2023 | The target was not achieved | Due to ack of LED Manager to oversee the KPI LED to non-performance | The Issue of Manager LED will be resolved in the first quarter of the new financial year |
|  | Budget (R) |  | R60 000 |  |  |  |
|  | Number of funding applications submitted for the establishment of an Abattoir | New | 1 funding applications submitted for the establishment of an Abattoir by 30 June 2023 | The target was not achieved | Due to ack of LED Manager to oversee the KPI LED to non-performance | The Issue of Manager LED will be resolved in the first quarter of the new financial year |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Heritage, Culture, Arts and Sports events held | New | 2 Heritage, Culture, Arts and Sports events held 30 March 2023 (Q1 & Q 3) | The target was not achieved | Due to ack of LED Manager to oversee the KPI LED to non-performance | The Issue of Manager LED will be resolved in the first quarter of the new financial year |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Reports on Eskom Electrification Programme & Projects submitted to Council | Existing | 4 reports on Eskom Electrification Programme & Projects submitted to Council (1 per quarter)) | 4 Reports on Eskom Electrification Programme & Projects were submitted to Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of planned & Emergency Maintenance projects undertaken on municipal facilities | 2 Maintenance Projects | 1 Maintenance Projects done by the 30 June 2023 | The target was not achieved | The contractor could not be appointed due change in management | The tender on appointment of maintenance contractor had to be re-Advertised and is closing 24 January 2023 |
|  | Budget (R) |  | R2 200 000 |  |  |  |
|  | Number of Indigent Household (HH) receiving Free Basic Electricity | 7 500 HH | 7 500 Free Basic Electricity collections per individual household by 30 June 2023 | 8 670 Free Basic Electricity collections per individual household were made | The over performance is due to the increased number of configured Household | N/A |
|  | Budget (R) |  | R 7 000 000 |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Reports on the implementation of Water Projects by DWA&S, NMMDM & Sedibeng noted by Council | Existing | 4 Water Projects Reports noted by Council (1 per quarter) | 4 Water Project Report were noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Reports on Waste Removal noted by Council | Existing | 4 Waste Removal Reports noted by Council (1 per quarter) | 4 Waste removal reports were noted by Council | N/A | N/A |
|  | Budget (R) |  | R2 200 000 |  |  |  |
|  | Number of Reports on Housing Projects Implemented by DHS noted by Council | Existing | 4 Housing Reports noted by Council (1 per quarter) | 4 Housing Report were noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Cemeteries Fenced and provided with VIP Toilet | 18 cemeteries fenced. | 1 Cemeteries fenced and provided with VIP Toilets (Lokaleng ) | The target was not achieved | 1st cemetery was completed and 2nd is on 80% completion. This was advertised as one project in form of combo and the delay in completion was due to late appointment of contractors | Internal Consequence Management Processes implemented |
|  | Budget (R) |  | R 1 900 000 |  |  |  |
|  | Number rehabilitated Existing Sports Complex | 2 Sports Complex | 1 Rehabilitated Existing Sports Complex Constructed and Completed (Soccer pitch earthworks complete) by 30 June 2023 (Mareetsane Village) | The target was not achieved | The site Establishment is Completed and the delay was due to late appointment of contractors | Internal Consequence Management Processes implemented |
|  | Budget( R) |  | R 7 172 550 |  |  |  |
|  | Number of Roads & Storm water constructed | 25km of road paved | 1km Roads & Storm water constructed & completed by 30 June 2023(Setlhwatlhwe and Ramabesa Phase 02) | The target was not achieved | The lack of performance was due to late appointment of contractors | Internal Consequence Management Processes implemented |
|  | Budget( R) |  | R 16 866 652. 56 |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of Audit Charter Plan developed & reviewed | 1 | Audit Charter & Plan developed by 31 December 2022 | 1 Audit Charter & Plan was developed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Audit Committee sittings held | 4 | 4 Audit Committee sittings held (1 per quarter) | 9 Audit Committee Sittings were held | The over performance was as a result of preparation for submission of AFS and Performance information as well as normal scheduled sittings | N/A |
|  | Budget (R) |  | R200 000 |  |  |  |
|  | Number of Internal Audits Conducted | 4 Internal Audit | 4 Internal Audits Conducted | 6 Internal Audit were conducted | The over performance was a result of preparation for submission of AFS and Performance information and special Verifications of employees | N/A |
|  | Budget (r) |  | Operational |  |  |  |
|  | Number of Internal Audit (IA) Plan Adopted by Audit Committee | 1 | 1 IA Plan developed. by 31 May 2023 | 1 IAP has been approved by the Committee | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |
|  | Number of Risk Management policy (RMP) Reviewed and adopted | Policy Existing | 1 Reviewed RMP by 31 May 2023 | The target was not achieved | Due to unavailability of a dedicated official and Risk Management Committee within the Municipality | The management with the assistance of the Audit Committee has resolved to establish the Risk Management Committee and also to have an official assisting in the Unit |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Internal Audit Reports Submitted to Audit Committee for Consideration | 4 | 4 Internal Audit Reports submitted to Audit Committee for consideration ( 1 per quarter) | 6 Internal Audit report has been submitted | The over performance was as result of submission of AFS and Performance information for submission to AG | N/A |
|  | Budget (R) |  | Operational |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE ACCOUNTABLE, EFFICIENT & TRANSPARENT ORGANISATION | Number of revised Risk Management Strategy (RMS) approved by Council | Strategy in Place | 1 Revised RMS by 31 May 2023 | The target was not achieved | The Municipality does not have a functional Risk Management Unit | Ratlou Local Municipality and Audit Committee had resolved to resuscitate the establishment of Risk Management committee and it is expected to be fully functional in the new financial year |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Revised Fraud and Corruption Strategy adopted by Council | Strategy in Place | 1 Revised Fraud & Corruption Strategy Adopted by Council by 30 June 2023 | The target was not achieved. | The Municipality does not have a functional Risk Management Unit | Ratlou Local Municipality and Audit Committee had resolved to resuscitate the establishment of Risk Management committee and it is expected to be fully functional in the new financial year |
|  | Budget (R) |  | Operational |  |  |  |
| PROMOTE GOOD GOVERNANCE | Number of MPAC Reports submitted to Council for noting | 4 | 4 MPAC Reports submitted to council for noting. (1 per quarter) | The target was not achieved | 1 MPAC report was submitted as there was no MPAC sitting held owing to the quorum | The Office of the Speaker to intervene in the matter |
|  | Budget (R) |  | R50 000 |  |  |  |
|  | Number of Support Training Conducted for MPAC & Rules Committee(Training on Roles & Responsibility) | 2 | 2 Support Training Conducted for MPAC & Rules Committee (Q2 & Q4 | The target was not achieved | 1 MPAC training was conducted and Rules Committee training was arranged for27 June 2023 and postponed due to urgent COGTA visit | The Support training has been rescheduled to August 2023 |
|  | Budget (R) |  | Same As Above |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE COMMUNITY PARTICIPATION | Number of Ward Committees Functional | 14 Ward Committees | 14 Functional Ward Committees | 14 Ward Committees are functional | N/A | N/A |
|  | Budget (R) |  | R2 604 000 |  |  |  |
|  | Number of Ward Committee reports noted by Council | Existing | 4 Reports on Ward Committees noted by Council | 4 Reports on Ward Committee were noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |
|  | Number of Ward Committees supplied with Stationery | 140 Ward Committees | 140 Ward Committees supplied with Stationery by 30 June 2023 | Th target was not achieved | The supply chain process was not completed | To be finalized in the Second quarter |
|  | Budget (R) |  | R100 000 |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE COMMUNITY PARTICIPATION | Number of Public Participation Events Supported | 4 events | 12 (3 x IDP/Budget/PMS, 3 x Annual Report, 2 x Imbizos & 4 x Ward Comm. Functions) | The target was not achieved. | 6 Public Participation events were supported as MPAC did not conduct their Public Participation events | N/A |
|  | Budget (R) |  | R100 000 |  |  |  |
|  | Number of Support Initiatives for Traditional Leaders Implemented | 4 Support Initiatives | 4 Support Initiatives for Traditional Leaders Implemented (1 per qurter) | 4 Support initiatives have been implemented | N/A | N/A |
|  | Budget (R) (R) |  | R 352 000 |  |  |  |
|  | Number of Dipitso tsa Baagi Held | 2 Diitso tsa Baagi | 2 Dipitso tsa Baagi Held (Q3 & Q4) | The target was not achieved | Due to tight schedule of the political office bearer | The meetings will be arranged for the new financial year |
|  | Budget (R) |  | R50 000 |  |  |  |
|  | Number of Youth Summit Held | 1 Youth Summit | 1 Youth Summit Held by 30 June 2023 | 1 Youth Summit was held | N/A | N/A |
|  | Budget (R) |  | R200 000 |  |  |  |
|  | Number of Youth Career Exhibition Held | 1 Youth Career Exhibition | 1 Youth Career Exhibition Held by 30 June 2023 | 1 Youth Career Exhibition was held | N/A | N/A |
|  | Budget (R) |  | As indicated above |  |  |  |
|  | Number of Youth Development Programmes Held | 4 Youth Development programmes | 4 Youth Development programmes held (1 per quarter) | 4 Youth Development programme was held | N/A | N/A |
|  | Budget (R) |  | As indicated above |  |  |  |
|  | Number of Disability Forum Meetings Held | 4 Disability Forum | 1 Disability Forum Meeting Held by 30 June 2023 | The Target was not achieved | 1 Disability Forum Meetings was Held, the planned forum meeting for quarter 2 did not materialize due unavailability of participants | N/A |
|  | Budget (R) |  | R 50 000 |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| ENHANCE COMMUNICATION | Number of Communication strategy reviewed and adopted by Ccouncil | Strategy in Place | 1 Communication Strategy Reviewed and adopted by 31 May 2022 | The target was not achieved | Communication strategies were not adopted because its part of the policy that we supposed to be adopted by Council. | The strategy will be reviewed in the next financial year |
|  | Budget (R) (R) |  | Operational |  |  |  |
|  | Number of Reports on Operational Tele Centres | 1 | 3 Operational Tele Centres( Tshidilamolo, Kraaipan, Setlagole) | 3 Telecenters are operational | N/A | N/A |
|  | Budget (R) (R) |  | R5700 000 |  |  |  |
|  | Number of Reports on Moderate and Assessment | 1 | 1 Moderate & Assessment noted by Council | 1 Report has been noted by Council | N/A | N/A |
|  | Budget (R) |  | Same As Above |  |  |  |
|  | Number of Graduation Ceremonies held | 1 Graduation ceremony | 1 Graduation Ceremonies held by 30 June 2023 | The Target was not achieved | The Municipality is awaiting the quality assurance report from SETA before the Graduation Ceremony could take place | Continuous follow-ups are being made |
|  | Budget (R) |  | Same As Above |  |  |  |
|  | Number of Accredited Tele centres | 1 | 1 Tele Centre Accredited by 30 June 2022 | 1 Telecentre has been accredited | N/A | N/A |
|  | Budget (R) |  | Same As Above |  |  |  |

| KPA: SPATIAL RATIONALE |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE SPATIAL PLANNING | Number of General Valuation Rolls implemented | 2012/2017 SDF | 1 General Valuation Roll implemented by 30 June 2023 | 1 General Valuation Roll has been implemented | N/A | N/A |
|  | Budget (R) |  | R1 320 000 |  |  |  |
|  | Number of Municipal Planning Tribunal appointed | New | 1 MPT appointed by 30 June 2023 | 1 Municipal Planning Tribunal has been appointed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |