9999999999999999999999999999999999999**zzzzzzzzzzzzzzzzzzzzzzzzzzzzzzz

RATLOU LOCAL MUNICIPALITY

3rd quarter report

PERIOD 01 JANUARY-31 MARCH 2023

OVERALL PERFORMANCE PER KEY PERFORMANCE AREA

|  | MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | MUNICIPAL FINANCIAL VIABILITY | LOCAL ECONOMIC DEVELOPMENT | INFRASTRUCTURE AND BASIC SERVICES | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | SPATIAL RATIONALE | OVERALL PERFORMANCE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL KPIs PLANNED FOR THE QUARTER | 11 | 12 | 03 | 04 | 15 | 01 | 46 |
| TOTAL ACHIEVED | 03 | 07 | The Unit did not report as required | 04 | 13 | The Unit did not report as required | 27 |
| TOTAL NOT ACHHIEVED | 08 | 05 | 03 | 0 | 02 | 01 | 19 |
| PERFORMANCE ON PERCENTAGES | 27% | 58% | 0% | 100% | 86% | 0% | 59% |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING & PERFORMANCE MANAGEMENT | Number of Developed/reviewed/amended IDP Adopted | 2022/2027 IDP | 2023/2024 IDP Adopted by 31 May 2023 | Project Phase Draft IDP Approved by 31st March 2023 | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention |
|  | Budget (r) |  | R 190 000 |  |  |  |  |
|  | Number of Developed & Approved SDBIP | 2017/2022 IDP | Service Delivery and Budget Implementation Plan Approved by 12 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | Same As Above |  |  |  |  |
|  | Number of IDP Rep forums held | 2021/2022 SDBIP | 2 IDP Representative forum meetings held (Q3 & 4) | 1 IDP Representative forum meeting held | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | 2022/2027 IDP & Budget Schedule Activities adopted by Council | 2017/2022 Schedule of Activities (IDP/Budget) | 1 IDP & Budget Schedule of Activities Adopted by 31 August 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | Number of Mid-term Assessment Held | 2021/2022 Mid-Term | 1 Mid Term Assessment held by 31 January 2023 | 1 Mid Term Assessment\eld | The Mid-Term assessment was successfully conducted by on 31 January 2023 | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING AND PERFORMANCE MANAGEMENT | Number of Strategic sessions held | 2020/2021 | 1 Strategic Planning Session held by 30 September 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | R 420 000 |  |  |  |  |
|  | Number of Annual Report approved by council | 2021/2022 Annual Report | 21/22 Annual Report Adopted by Council by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | PMS Policy developed & adopted | 2016/2017 PMS policy | 1 PMS Policy developed & adopted by Council by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE TECHNOLOGY EFFICIENCY | Number of IT Master Plans Developed & adopted | 2019/2020 | 1 IT Master Plans Developed & adopted by Council by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | R 150 000 |  |  |  |  |
|  | Number of Reports on Updated Municipal Website | 2021/2022 SDBIP | 2 Reports on Updated Municipal Website (1 Per quarter) | 1 Report on Updated Municipal Website | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention |
|  | Budget (r) |  | R100 000 |  |  |  |  |
|  | Number of reports on IT, Telephones complains received and submitted to Council for noting | Existing | 2 Reports on IT, Telephones complains received and submitted to Council for noting. (1 Per quarter) | 1 Report on IT, Telephones complains received and submitted to Council for noting | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention |
|  | Budget (r) |  | R 2 650 000 |  |  |  |  |
|  | Number of Reports on Software and Hardware updated | Existing | 2 Reports on Software & Hardware updates (1 Per quarter) | 1 Report on Software & Hardware updates | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention |
|  | Budget (r) |  | R 199 205 |  |  |  |  |
|  | Number of Operational Disaster and Business Continuity Plans Reviewed | Existing | 1 Operational Disaster and Business Continuity Plans Reviewed by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (r) |  | R 350 000l |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| RETAIN & RECRUIT TALENTED EMPLOYEES | Number of Revised Policies adopted by Council | 6 Policies | 24 HR Policies reviewed & adopted. 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
|  | Number of Human Resource Development Strategy Developed & Reviewed | Existing | 1 Human Resource Development Strategy Developed & Reviewed by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
| PROMOTE INNOVATION LEARNING AND GROWTH | Number of 2022/2023 Workplace Skills Development Plan (WSDP) Developed & submitted to LGSETA | 2021/2022 WSDP | 1 WSDP submitted to LGSETA by 30 April 2023 | WSDP submitted to LGSETA. | The WSDP has been submitted with in the required period | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
|  | Number of applicants benefiting from the bursary fund | 6 Bursars | 10 Bursars benefiting from the Bursary fund by 30 March 2023 | 10 Bursars benefitted from the Bursary fund | The target was not achieved | The policy regulating the allocation of Bursaries is not yet reviewed | The policy will be reviewed during the last quarter of the current financial year. |
|  | Budget ® |  | R 400 000 |  |  |  |  |
|  | Number of Workplace Skills Development Plan targets achieved | New | 15 Workplace Skills Development Plan targets achieved. By 30 June 2023 | 4 Workplace Skills Development Plan targets achieved | The target was not achieved | The policy regulating the allocation of Bursaries is not yet reviewed | The policy will be reviewed during the last quarter of the current financial year. |
|  | Budget ® |  | R 630 000 |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| ACHIEVE EMPLOYMENT EQUITY | Number Employment Equity Plan Developed & submitted to the dept of labour | Employment Equity Plan 2021/2022 | 1 EEP completed and submitted by 15 January 2023 | 1 Complete & Submitted EEP | The Employment Equity Plan was submitted on 12 January 2023 | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
|  | Number of Employment Equity targets achieved | 2 Employment equity Targets | 2 EEP Targets achieved by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget ® |  | Operational |  |  |  |  |
| ACHIEVE POSITIVE EMPLOYEE CLIMATE | Number of LLF Meetings held | 3 LLF meeting | 6 LLF Meetings held by 30 June 2023 | 1 LLF Meeting held | Not achieved | The LLF could not sit due to continuous change in Senior Management positions | The Planned LLF will be held in quarter 4 |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of employees that have signed Code of conduct | 212 employees | 230 employees that have signed Code of conduct by 31 July 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Promote Financial Accountability | 2023/2024 Budget approved by Council | 2022/2023 Budget | 2023/2024 Budget approved by 31 May 2023 | Draft Budget by 29 March 2023 | Draft budget was approved on 30 March 2023 | N/A | N/A |
|  | BUDGET (R) |  | OPERATIONAL |  |  |  |  |
|  | Number of Budget Related policies* adopted by Council | 13 Policies | 16 Policies Adopted by 31 May 2023 | 16 Draft Policies Noted by Council | Draft policies were adopted together with Draft budget | N/A | N/A |
|  | BUDGET (R) |  | OPERATIONAL |  |  |  |  |
|  | 2022/2023 Adjustment Budget Approved by Council | 2022122 Adjustment budget approved | 2022/2023 Adjustment Budget Approved by 28 February 2023 | 2022/2023 Adjustment Budget Approved | 2022/2023 Adjustment budget approved on 28 February 2023 | N/A | N/A |
|  | BUDGET (R) |  | OPERATIONAL |  |  |  |  |
|  | Council approved 2022/203 Annual Financial Statements (AFS) submitted to the Office of the Auditor-General (A-G) | 2020/2021 Audited AFS | AFS submitted to A-G by 30 August 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET (R) |  | R1 900 000 |  |  |  |  |
|  | Number of Supply Chain Management reports submitted to council | Existing | 4 Supply Chain Management reports submitted to council for noting. (1 Per quarter) | 1 Supply Chain Management report submitted to council for noting. | 1 Supply Chain Management report has been submitted to council for noting. | N/A | N/A |
|  | BUDGET (R) |  | OPERATIONAL |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Credit Control Policy Reviewed | Policy Existing | 1 Credit control Policy reviewed by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number Credit control implemented | Policy Existing | 1 Credit control implemented by 30 September 22 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number Indigent Policies Reviewed | Policy Existing | 1 Indigent Policy Reviewed by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Indigent Policies implemented | Policy Existing | 1 Indigent Policies implemented by 30 September 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Consumer Awareness campaigns held | New | 2 Consumer Awareness campaigns held by 30 March 2023 | 1 Consumer Awareness campaigns held | The target was not achieved | The Awareness Campaign that was scheduled for the 28 March 2023 was not held due to commitments that could not be avoided | The awareness has been re-scheduled to the 16th May 2023 |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of MPRA meetings held | Existing | 3 MPRA meetings held (1 Per quarter) | 1 MPRA meetings held | The Target was not achieved | Due to the unresolved dispute by rate payers | The Municipality has written a letter to COGTA to seek intervention |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | % Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 95% | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 95% Collection of billed revenue | Rent & Electricity = 67.77 % Rates & Taxes 91.22% Licencing Commission = 72.58% Average = 77.19% | There was a resolution taken during Midterm Engagement with Provincial Treasury on Farmers Disputes Accounts, that Department of COGTA must assist the municipality to close the disputes by providing the final advice and recommendation on the disputes and the letter was submitted during March 2023 | The Municipality is still awaiting a response from the Department of COGTA |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Achieve Clean Audit | Number of quarterly AFS submitted to Council | New | 4 quarterly AFS submitted to Council for noting (1 per quarter) | 1 quarterly AFS submitted to Council for noting | The target was not achieved | The Municipality is using the services of the Service provider and a result, access to information remains a serious challenge | The Municipality is in a process of creating a new file internally |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Audit Plans Developed to address Auditor – General (A-G Queries adopted by Council | 2021/22 Audit Action Plan | 1 Audit Action Plan Developed by 31 January 2023 | 1 Audit Action Plan Developed | The Audit Action Plan has been developed | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on the Implementation of the Audit Action Plan noted by Council | Existing | 2 Reports on the Implementation of the Audit Action Plan noted by Council 3rd and 4th Quarter | 1 Report on the Implementation of the Audit Action Plan noted by Council. 3rd and 4th Quarter | 1 Report on the implementation of Audit Action Plan has been submitted and adopted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of PAAP reports included in the Management Meeting | PAAP Progress Report | 2 PAAP reports included in the Management Meeting (1 per quarter) | 1 PAAP reports included in the Management Meeting | The target was not achieved | Due to internal Management not holding their meeting as required | The feed on PAAP has been arranged to be accessed online to improve progress |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| Improve Assets Management | Number of Asset registers updated | Existing | 1 Asset registers updated. 30 September 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of reports on assets verification noted by Council | Existing | 4 reports on assets verification noted by Council (1 per quarter) | 1 Report on assets verification noted by Council | 1 Report on assets verification was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Asset committee established | Existing | 1 Asset committee established by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of meetings held of the asset committee | Existing | 1 Asset Committee meeting by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Jobs created through Expanded Public Works Programme, Community Workers Programme, Capital Projects and other Local Economic Development initiatives | 1000 Jobs | 1000 Jobs created 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R31 497 250 (MIG) |  |  |  |  |
|  |  |  | R1 239 000 EPWP |  |  |  |  |
|  | Number of Billboards erected | Information Boards | - Billboards erected in Ratlou South & North by 30 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 70 000 |  |  |  |  |
|  | Number of LED & Tourism Strategies Developed & Adopted | 2012-2017 strategy | 1 LED Strategy Developed & Adopted by Council by 30 June 2023 | Draft LED Strategy | No report was submitted for this target | The matter has been brought to MM’s attention for intervention | No report was submitted for this target |
|  | Budget (R) |  | R 1 230 000 |  |  |  |  |
|  | Number of SMMEs/Cooperatives support initiatives | 4 Support initiatives | 6 Support initiatives by 30 June 2023 ( Funding, Business Plan Development, exhibitions, Training & Workshops) | 2 Support initiative | No report was submitted for this target | The matter has been brought to MM’s attention for intervention | No report was submitted for this target |
|  | Budget (R) |  | R500 000 |  |  |  |  |
|  | Number of reports on the implementation of the SLP | Existing | 2 reports on the implementation of the SLP (1 per quarter) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Signage & Branding Erected (Information Boards) | 10 Signage & Branding | 10 Signage & Branding Erected by (Information Boards)30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET (R) |  | R60 000 |  |  |  |  |
|  | Number of funding applications submitted for the establishment of an Abattoir | New | 1 funding applications submitted for the establishment of an Abattoir by 30 June 2023 | funding applications submitted for the establishment of an Abattoir | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention for intervention |
|  | BUDGET (R) |  | OPERATIONAL |  |  |  |  |
|  | Number of Heritage, Culture, Arts and Sports events held | New | 2 Heritage, Culture, Arts and Sports events held 30 March 2023 (Q1 & Q 3) | 1 Heritage, Culture, Arts and Sports events held | The target was not achieved | No report was submitted for this target | The matter has been brought to MM’s attention for intervention |
|  | BUDGET (R) |  | OPERATIONAL |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Reports on Eskom Electrification Programme & Projects submitted to Council | Existing | 4 reports on Eskom Electrification Programme & Projects submitted to Council (1 per quarter)) | 1 Report on Eskom Electrification Programme & Projects | 1 Report Eskom on Electrification Programme & Projects was submitted to Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of planned & Emergency Maintenance projects undertaken on municipal facilities | 2 Maintenance Projects | 1 Maintenance Projects done by the 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R2 200 000 |  |  |  |  |
|  | Number of Indigent Household (HH) receiving Free Basic Electricity | 7 500 HH | 7 500 Free Basic Electricity collections per individual household by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 7 000 000 |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Reports on the implementation of Water Projects by DWA&S, NMMDM & Sedibeng noted by Council | Existing | 4 Water Projects Reports noted by Council (1 per quarter) | 1 Water Project Report | 1 Water Project report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on Waste Removal noted by Council | Existing | 4 Waste Removal Reports noted by Council (1 per quarter) | 1 Waste removal Report | 1 Waste removal report was noted by Council | N/A | N/A |
|  | Budget (R) |  | R2 200 000 |  |  |  |  |
|  | Number of Reports on Housing Projects Implemented by DHS noted by Council | Existing | 4 Housing Reports noted by Council (1 per quarter) | 1 Housing Report | 1 Housing report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES & INFRASTRUCTURE | Number of Cemeteries Fenced and provided with VIP Toilet | 18 cemeteries fenced | 1 Cemeteries fenced and provided with VIP Toilets (Lokaleng ) | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET (R) |  | R 1 900 000 |  |  |  |  |
|  | Number rehabilitated Existing Sports Complex | 2 Sports Complex | 1 Rehabilitated Existing Sports Complex Constructed and Completed (Soccer pitch earthworks complete) by 30 June 2023 (Mareetsane Village) | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET( R) |  | R 7 172 550 |  |  |  |  |
|  | Number of Roads & Storm water constructed | 25km of road paved | 1km Roads & Storm water constructed & completed by 30 June 2023(Setlhwatlhwe and Ramabesa Phase 02) | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET( R) |  | R 16 866 652. 56 |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of Audit Charter Plan developed & reviewed | 1 | Audit Charter & Plan developed by 31 December 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Audit Committee sittings held | 4 | 4 Audit Committee sittings held (1 per quarter) | 1 Audit Committee sittings | 3 Audit Committee Sittings were held | The reason for deviation was caused by the contents of the internal audit report presented to audit committee on the 17 March 2023. | N/A |
|  | Budget (R) |  | R200 000 |  |  |  |  |
|  | Number of Internal Audits Conducted | 4 Internal Audit | 4 Internal Audits Conducted | 1 Internal Audits Conducted | 1 Audit Conducted (Performance Audit) | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | Number of Internal Audit (IA) Plan Adopted by Audit Committee | 1 | 1 IA Plan developed by 31 May 2022 | 1 Draft IA in place | 1 Draft IA is in place | N/A | N/A |
|  | Budget (r) |  | Operational |  |  |  |  |
|  | Number of Risk Management policy (RMP) Reviewed and adopted | Policy Existing | 1 Reviewed RMP by 31 May 2022 | 1 Draft RMP in place | 1 Draft RMP is in place | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Internal Audit Reports Submitted to Audit Committee for Consideration | 4 | 4 Internal Audit Reports submitted to Audit Committee for consideration ( 1 per quarter) | 1 Internal Audit Report submitted | 2 Internal Audit Reports Submitted to Audit Committee on the 17 March 2023 | The reason for overperformance was due to a special Audit conducted on verification of employees. | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE ACCOUNTABLE, EFFICIENT AND TRANSPARENT ORGANISATION | Number of revised Risk Management Strategy (RMS) approved by Council | Strategy in Place | 1 Revised RMS by 31 May 2023 | 1 Draft Revised RMS in place | 1 Draft Revised RMS is in place | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Revised Fraud and Corruption Strategy adopted by Council | Strategy in Place | 1 Revised Fraud & Corruption Strategy Adopted by Council by 30 June 2023 | 1 Draft Fraud & Corruption Strategy in place | 1 Draft Fraud & Corruption Strategy is in place | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of MPAC Reports submitted to Council for noting | 4 | 4 MPAC Reports submitted to council for noting. (1 per quarter) | 1 MPAC Report submitted to Council | 1 MPAC report has been submitted to Council | N/A | N/A |
|  | BUDGET (R) |  | R50 000 |  |  |  |  |
|  | Number of Support Training Conducted for MPAC & Rules Committee(Training on Roles & Responsibility) | 2 | 2 Support Training Conducted for MPAC & Rules Committee (Q2 & Q4 | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET (R) |  | Same As Above |  |  |  |  |
| PROMOTE COMMUNITY PARTICIPATION | Number of Ward Committees Functional | 14 Ward Committees | 14 Functional Ward Committees | 14 Functional Ward Committees | 14 Ward committees are functional | N/A | N/A |
|  | BUDGET (R) |  | R2 604 000 |  |  |  |  |
|  | Number of Ward Committee reports noted by Council | Existing | 4 Reports on Ward Committees noted by Council | 1 Report on Ward Committees | 1Wad Committee report has been noted by Council | N/A | N/A |
|  | BUDGET (R) |  | Operational |  |  |  |  |
|  | Number of Ward Committees supplied with Stationery | 140 Ward Committees | 140 Ward Committees supplied with Stationery by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | BUDGET (R) |  | R100 000 |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | Performance Indicator | Baseline | Revised Annual Target | Quarter 3 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE COMMUNITY PARTICIPATION | Number of Public Participation Events Supported | 4 events | 12 (3 x IDP/Budget/PMS, 3 x Annual Report, 2 x Imbizos & 4 x Ward Comm. Functions) | 3 x Annual Report 1 x Ward Committed Function | The target was not achieved. | MPAC did not adhere to the scheduled dates as resolved by Council | The office to reschedule the dates for public participation |
|  | Budget (R) |  | R100 000 |  |  |  |  |
|  | Number of Support Initiatives for Traditional Leaders Implemented | 4 Support Initiatives | 4 Support Initiatives for Traditional Leaders Implemented (1 per qurter) | 1 Support Initiative | 1 Support Initiative has been implemented | N/A | N/A |
|  | Budget (R) (R) |  | R 352 000 |  |  |  |  |
|  | Number of Dipitso tsa Baagi Held | 2 Diitso tsa Baagi | 2 Dipitso tsa Baagi Held (Q3 & Q4) | 1 Dipitso tsa Baagi Held | The target was not achieved | Due to tight schedule in Mayor’s Office | To be addressed in the last quarter of the current financial year |
|  | Budget (R) |  | R50 000 |  |  |  |  |
|  | Number of Youth Summit Held | 1 Youth Summit | 1 Youth Summit Held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R200 000 |  |  |  |  |
|  | Number of Youth Career Exhibition Held | 1 Youth Career Exhibition | 1 Youth Career Exhibition Held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | As indicated above |  |  |  |  |
|  | Number of Youth Development Programmes Held | 4 Youth Development programmes | 4 Youth Development programmes held (1 per quarter) | 1 Youth Development programme held | 1 Youth Development programme was held | N/A | N/A |
|  | Budget (R) |  | As indicated above |  |  |  |  |
|  | Number of Disability Forum Meetings Held | 4 Disability Forum | 1 Disability Forum Meeting Held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 50 000 |  |  |  |  |

KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION. Objectives; Performance Indicator; Baseline; Revised Annual Target; Quarter 3 Target; Actual Performance; Reasons for variance (under / over performance); Corrective measures. ENHANCE COMMUNICATION; Number of Communication strategy reviewed and adopted by council; Strategy in Place; 1 Communication Strategy Reviewed and adopted by 31 May 2022; Not a target for this quarter; N/A; N/A; N/A. Budget (R) (R); Operational. Number of Reports on Operational Tele Centres; 1; 3 Operational Tele Centres( Tshidilamolo, Kraaipan, Setlagole); 1 Operational Tele Centre; 1 Tele Centre is operational; N/A; N/A. Budget (R) (R); R5700 000. Number of Reports on Moderate and Assessment; 1; 1 Moderate & Assessment noted by Council; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Same As Above. Number of Graduation Ceremonies held; 1 Graduation ceremony; 1 Graduation Ceremonies held by 30 June 2023; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Same As Above. Number of Accredited Tele centres; 1; 1 Tele Centre Accredited by 30 June 2022; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Same As Above. SPATIAL RATIONALE. Objectives; Performance Indicator; Baseline; Revised Annual Target; Quarter 3 Target; Actual Performance; Reasons for variance (under / over performance); Corrective measures. IMPROVE SPATIAL PLANNING; Number of General Valuation Rolls implemented; 2012/2017 SDF; 1 General Valuation Roll implemented by 30 June 2023; Submission of the Roll to the Municipal Manager; The target was not achieved; No report was submitted for this target; The matter has been brought to MM’s attention. Budget (R); R1 320 000. Number of Municipal Planning Tribunal appointed; New; 2 1 MPT appointed by 30 June 2023; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Operational.