9999999999999999999999999999999999999**zzzzzzzzzzzzzzzzzzzzzzzzzzzzzzz

RATLOU LOCAL MUNICIPALITY

1st quarter report

PERIOD 1 JULY 2022 – 30 SEPTEMBER 2022

OVERALL PERFORMANCE PER KEY PERFORMANCE AREA

|  | MUNICIPAL TRANSFORMATION AND ORGANIZATIONAL DEVELOPMENT | MUNICIPAL FINANCIAL VIABILITY | LOCAL ECONOMIC DEVELOPMENT | INFRASTRUCTURE AND BASIC SERVICES | GOOD GOVERNANCE AND PUBLIC PARTICIPATION | SPATIAL RATIONALE | OVERALL PERFORMANCE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL KPIs PLANNED FOR THE QUARTER | 13 | 13 | 04 | 06 | 10 | 02 | 48 |
| TOTAL ACHIEVED | 04 | 06 | 02 | 05 | 09 | 01 | 26 |
| TOTAL NOT ACHHIEVED | 09 | 07 | 02 | 01 | 01 | 01 | 22 |
| PERFORMANCE ON PERCENTAGES | 30% | 46% | 50% | 83% | 90% | 50% | 54% |

| KPA: MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING & PERFORMANCE MANAGEMENT | Number of Developed/reviewed/amended IDP Adopted | 2022/2027 IDP | 2023/2024 IDP Adopted by 31 May 2023 | IDP & Budget Schedule of Activities Adopted | The process plan has adopted on 30 August 2022 | N/A | N/A |
|  | Budget (R) |  | R 180 000 |  |  |  |  |
|  | Number of Developed & Approved SDBIP | 2017/2022 IDP | Service Delivery and Budget Implementation Plan Approved by 12 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Same as above |  |  |  |  |
|  | Number of IDP Rep forums held | 2020/2021 SDBIP | 4 IDP Representative forum meetings held (1 per quarter) | 1 IDP Representative forum meeting held | 0 IDP Representative forum meeting held | An advert was issued calling for members of the public to register as Forum Members, however, no registration forms were received | During the 2nd Forum, invitations will be issued to members whose contact details are readily available. |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | 2022/2027 IDP & Budget Schedule Activities adopted by Council | 2017/2022 Schedule of Activities (IDP/Budget) | IDP & Budget Schedule of Activities Adopted by 31 August 2022 | IDP & Budget Schedule of Activities Adopted by 31 August 2022 | The IDP & Budget Schedule of activities has been adopted by Council on the 30 August 2022 | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Mid-term Assessment Held | 1 | 1 Mid Term Assessment held by 31 January 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| MUNICIPAL TRANSFORMATION AND INSTITTUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE PLANNING & PERFORMANCE MANAGEMENT | Number of Strategic sessions held | 2019/2020 | 1 Strategic Planning Session held by 30 November 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 260 000 |  |  |  |  |
|  | 21/222 Annual Report approved by council | 2020/2021 Annual Report | 2021/22 Annual Report Adopted by Council by 31 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R100 000 |  |  |  |  |
|  | PMS Policy developed & adopted | 2020/2021 SDBIP | 1 PMS Policy developed & adopted by Council by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | No of training workshops on PMS | Policy Exist | 2 training workshops on PMS to be held | 1 training workshop on PMS held | The target was not achieved | Due to Moratorium on implementation of performance management as per National COGTA Circular 12 of 2022 on new staff regulations | To be implemented once the moratorium is lifted on the 01 July 2023 |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE TECHNOLOGY EFFICIENCY | Number of IT Master Plans Developed & adopted | 2019/2020 | 1 IT Master Plans Developed & adopted by Council by 30 November 2022 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 100 000 |  |  |  |  |
|  | Number of Reports on Updated Municipal Website | 2020/2021 SDBIP | 4 Reports on Updated Municipal Website | 1 Report on Updated Municipal Website | 0 Report on updated Municipal Website has been submitted | The report was not submitted due lack of internal capacity within the unit | The Municipality to fast track the process of appointment of a Unit Manager |
|  | Budget (R) |  | R 900 000 |  |  |  |  |
|  | Number of reports on IT, Telephones complains received and submitted to Council for noting | 1 Bosberaad held | 4 reports on IT, Telephones complains received and submitted to Council for noting | 1 Reports on IT, Telephones complains received and submitted to Council for noting | 0 Report on IT, Telephones complains has been submitted to Council for noting | The report was not submitted due lack of internal capacity within the unit | The Municipality to fast track the process of appointment of a Unit Manager |
|  | Budget (R) |  | R 3 500 000 |  |  |  |  |
|  | Number of Reports on Software and Hardware updated | Existing | 4 Reports on Software & Hardware updates | 1 Report on Software & Hardware updates | 0 Report on Software & Hardware updates have been submitted | The report was not submitted due lack of internal capacity within the unit | The Municipality to fast track the process of appointment of a Unit Manager |
|  | Budget (R) |  | R 640 000 |  |  |  |  |
|  | Number of Operational Disaster and Business Continuity Plans Reviewed | Existing | 1 Operational Disaster and Business Continuity Plans Reviewed by 30 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 400 000l |  |  |  |  |

| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives |  | Performance Indicator | Baseline |  | Annual Target |  | Quarter 1 Target |  | Actual Performance |  | Reasons for variance (under / over performance) |  | Corrective measures |  |
| RETAIN & RECRUIT TALENTED EMPLOYEES |  | Number of Revised Policies adopted by Council | 6 Policies |  | 24 HR Policies reviewed & adopted 30 June 2023 |  | Not a target for this quarter |  | N/A |  | N/A |  | N/A |  |
|  |  | Budget (R) |  |  | Operational |  |  |  |  |  |  |  |  |  |
|  |  | Number of Human Resource Development Strategy Developed & Reviewed | Existing |  | 1 Human Resource Development Strategy Developed & Reviewed by 30 September 2022 |  | 1 Human Resource Development Strategy Developed & Reviewed |  | The Human Resource Strategy has not been reviewed |  | The Councill has differed all the strategic Plan resolutions which include reviewing of policies and strategies. |  | All policies will be reviewed and adopted in second quarter |  |
|  |  | Budget (R) |  |  | Operational |  |  |  |  |  |  |  |  |  |
|  |  | Number of 2022/2023 Workplace Skills Development Plan (WSDP) Developed & Adopted by Council | 2019/2020 WSDP |  | 1 WSDP adopted by 30 April 2023 |  | Establish Training Committee |  | The Committee has been established |  | N/A |  | N/A |  |
|  |  | Budget (R) |  |  | Operational |  |  |  |  |  |  |  |  |  |
| PROMOTE INNOVATION LEARNING AND GROWTH |  | Number of applicants benefiting from the bursary fund | 6 |  | 10 Bursars by 30 March 2023 |  | Not a target for this quarter |  | N/A |  | N/A |  | N/A |  |
|  |  | Budget (R) |  |  | R 400 000 |  |  |  |  |  |  |  |  |  |
|  |  | Workplace Skills Development Plan targets achieved | New |  | 15 Workplace Skills Development Plan targets achieved |  | 3 Workplace Skills Development Plan targets achieved |  | Two (2) Workplace Skills Development Plan targets were achieved |  | The training for newly appointed Mayor and Speaker’s drivers could not continue due to tight schedule in those offices |  | The training will be implemented during the second quarter |  |
|  |  | Budget (R) |  |  | R 630 000 |  |  |  |  |  |  |  |  |  |
|  |  | Number of Skills Audit Conducted | Existing |  | 1 Skills Audit conducted |  | 1 Skills Audit conducted |  | The target was not achieved |  | Due to Moratorium on implementation of performance management as per National COGTA Circular 12 of 2022 on new staff regulations. |  | To be implemented once the moratorium is lifted on the 01 July 2023 |  |
|  |  | Budget (R) |  |  | Operational |  |  |  |  |  |  |  |  |  |
| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objectives | Performance Indicator |  |  | Baseline |  | Annual Target |  | Quarter 1 Target |  | Actual Performance |  | Reasons for variance (under / over performance) |  | Corrective measures |
| ACHIEVE EMPLOYMENT EQUITY | Number Employment Equity Plan Developed & submitted to the dept. of labour |  |  | Employment Equity Plan |  | 1 EEP completed and submitted by 15 January 2023 |  | Not a target for this quarter |  | N/A |  | N/A |  | N/A |
|  | Budget (R) |  |  |  |  | Operational |  |  |  |  |  |  |  |  |
|  | Employment Equity targets achieved |  |  | Employment Equity Plan in place |  | 2 EEP Targets achieved by 30 June 2023 |  | Not a target for this quarter |  | N/A |  | N/A |  | N/A |
|  | Budget (R) |  |  |  |  | Operational |  |  |  |  |  |  |  |  |
| ACHIEVE POSITIVE EMPLOYEE CLIMATE | Number of LLF Meetings held |  |  | 3 |  | 6 LLF Meetings held by 30 June 2023 |  | 2 LLF Meeting held |  | 0 LLF meeting was held |  | Due to unavailability and commitments of the Accounting Officer during the reporting period |  | LLF meetings will be held in quarter two |
|  | Budget (R) |  |  |  |  | Operational |  |  |  |  |  |  |  |  |
|  | Number of employees that have signed Code of conduct |  |  | 212 |  | 230 employees that have signed Code of conduct by 31 July 2022 |  | 230 employees that have signed Code of conduct |  | The Target has been achieved |  | N/A |  | N/A |
|  | Budget (R) |  |  |  |  | Operational |  |  |  |  |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE FINANCIAL ACCOUNTABILITY | 2023/2024 Budget approved by Council | 2022/2023 Budget | 2023/2024 Budget approved by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Budget Related policies* adopted by Council | 13 Policies | 13 Policies Adopted by 29 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | 2022/2023 Adjustment Budget Approved by Council | 2021/22 Adjustment budget approved | Approved 2022/2023 Adjustment Budget by 28 February 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Council approved 2019/2020 Annual Financial Statements (AFS) submitted to the Office of the Auditor-General (A-G) | 2018/2019 Audited AFS | AFS submitted to A-G by 30 August 2022 | Compiled & Submitted AFS by the 31 August 2022 | The Annual Financial Statement were submitted to Auditor-General on 31 August 2022 | N/A | N/A |
|  | Budget (R) |  | R 1 500 000 |  |  |  |  |
|  | Number of Supply Management reports submitted to council | Existing | 4 Supply Management reports submitted to council for noting (1 per quarter) | 1 Supply Chain Management report submitted to council for noting | 1 Supply Chain Management report was submitted to council for noting | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| REVENUE ENHANCEMENT | Number of Credit Control Policy Reviewed | Policy Existing | 1 Credit control Policy reviewed by 30 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number Credit control implemented | Policy Existing | 1 Credit control implemented 31 by July 22 | 1 Credit control implemented | 1 Credit control has been implemented | N/A | N/A |
|  | Budget (R) |  | R60 000 |  |  |  |  |
|  | Number Indigent Policies Reviewed | Policy Existing | 1 Indigent Policy Reviewed by 30 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Indigent Policies implemented | Policy Existing | 1 Indigent Policies implemented by 01 July 2022 | 1 Indigent Policies implemented | 1 Indigent policy has been implemented | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
|  | Number of Consumer Awareness campaigns held | New | 2 Consumer Awareness campaigns held | 1 Consumer Awareness campaigns held | 0 Consumer Awareness campaigns were held | The Municipality could not conduct the awareness due to systems vendor challenges for capturing of billing interest | To ensure that Awareness Campaign is held in the Quarter 2. |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of MPRA meetings held | Existing | 4 MPRA meetings held | 1 MPRA meetings held | 0 MPRA meetings were held | The MPRA Meeting was not held this quarter due to unprocessed last step of Accounts Spreadsheets of Farmers disputes. | The Municipality to address the Service Provider payment issue for finalisation of the dispute Accounts Spread Sheets. |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | % Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 35% | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 95% Collection of Billed Revenue | Rent & Electricity = 34.35 % Rates & Taxes = 2.47 % Licencing Commission = 0% Average = 12.27% | Account spread sheets for Disputes Accounts not yet processed. | The Municipality is currently addressing the processing of the Account Spread sheets into the System and the dispute will be resolved. |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINICIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| ACHIEVE CLEAN AUDIT | Number of quarterly AFS submitted to Council | New | 4 quarterly AFS submitted to Council for noting (1 per quarter) | 1 quarterly AFS submitted to Council for noting | 0 Quarterly AFS submitted to Council | The Municipality is awaiting CaseWare File from the Service Provider | The report will be compiled and submitted to Council in quarter 2 |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Audit Plans Developed to address Auditor – General (A-G Queries adopted by Council | 2020/21 Audit Action Plan | 1 Audit Action Plan Developed by 31 January 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on the Implementation of the Audit Action Plan noted by Council | Existing | 2 Reports on the Implementation of the Audit Action Plan noted by Council 3nd and 4th Quarter | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of PAAP reports included in the Management Meeting | PAAP Progress Report | 4 PAAP reports included in the Management Meeting (1 per quarter) | 1 PAAP reports included in the Management Meeting | 0 PAAP reports were included in the Management meeting | There was no Management Meeting Held | To ensure that PAAP is included in the subsequent management meeting agenda |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: FINICIAL VIABILITY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| IMPROVE ASSETS MANAGEMENT | Number of Asset registers updated | Existing | 1 Asset registers updated | 1 Asset registers updated | 1 Asset register was updated | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of reports on assets verification noted by Council | Existing | 4 reports on assets verification noted by Council | 1 report on assets verification noted by Council | 1 report on assets verification was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Asset committee established | Existing | 1 Asset committee established | 1 Asset committee established | 0 Asset committee was established | The committee was not established due to change of Acting Senior Managers | The committee will be established in the 2nd quarter |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of meetings held of the asset committee | Existing | 4 meetings held of the asset committee | 1 meeting of the asset committee held | 0 meeting of the asset committee held | There was no Asset committee in place | Meeting will be held on the 2nd quarter |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Jobs created through Expanded Public Works Programme, Community Workers Programme, Capital Projects and other Local Economic Development initiatives | 1000 | 1000 Jobs created | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R29 400 000 (MIG) R1 239 000 (EPWP) |  |  |  |  |
|  | Number of Billboards erected | Information Boards | 2 Bill boards erected in Ratlou South & North by 30 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 70 000 |  |  |  |  |
|  | Number of LED & Tourism Strategies Developed & Adopted | 2012-2017 | 1 LED Strategy Developed & Adopted by Council by 30 June 2023 | Advertisement | 0 LED Strategy was developed | Due to lack of proper budgeting. | The target to be reprioritized during budget adjustment |
|  | Budget (R) |  | R 500 000 |  |  |  |  |
|  | Number of SMMEs/Cooperatives support initiatives | 4 | 6 Support initiatives by 30 June 2023 (Funding, Business Plan Development, Exhibitions, Training & Workshops) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 500 000 |  |  |  |  |
|  | Number of reports on the implementation of the SLP | Existing | 4 reports on the implementation of the SLP (1 per quarter) | 1 report on the implementation of the SLP | 1 Report on the implementation of the SLP was submitted | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of LED Exhibitions held | New | 1 LED Exhibitions held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Signage & Branding Erected (Information Boards) | New | 10 Signage & Branding Erected by 30 June 2021 (Information Boards) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R60 000 |  |  |  |  |
|  | Number of reports on Profiled Lodges, Game Lodges & B&Bs | New | 4 Reports on Profiled Lodges, Game Lodges & B&Bs | 1 Report on Profiled Lodges, Game Lodges & B&Bs | 0 Report on profiling was made | The Owners of these establishment are not cooperative to share the information needed | The intervention has to be sought from the relevant authorities. |
|  | Budget( R) |  | Operational |  |  |  |  |
|  | Number of Municipal Tourism profiles developed and adopted | New | 1 Municipal Tourism profile developed and adopted by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget( R) |  | Operational |  |  |  |  |
|  | Number of funding applications submitted for the establishment of an Abattoir | New | 1 funding applications submitted for the establishment of an Abattoir by 30 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget(R) |  | Operational |  |  |  |  |

| KPA: LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE LOCAL ECONOMIC DEVELOPMENT & JOB CREATION | Number of Land Care Development programmes held | New | 2 Land Care Development Projects held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget(R) |  | Operational |  |  |  |  |
|  | Number of LED Hubs/SMME STALLS Constructed | Existing | 5 LED Hubs/SMME STALLS Constructed by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Heritage, Culture, Arts and Sports events held | Existing | 2 Heritage, Culture, Arts and Sports events held | 1 Heritage, Culture, Arts and Sports events held | 1 Event was held | N/A | N/A |
|  | Budget (R) |  | R70 000 |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES AND INFRASTRUCTURE | Km of gravel roads maintained | 16.4 km | 5 km length of maintained gravel roads by 30 June 2020 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 400 000 |  |  |  |  |
|  | Number of Reports on Serviced and Maintained High Mast & Flood Lights | 9 Reports | 6 Reports on Serviced and Maintained High Mast & Flood Lights by 30 June 2021 | 1 report on Serviced and Maintained High Mast & Flood Lights | 1 Report on Serviced and Maintained high Mast & Flood Lights was submitted | N/A | N/A |
|  | Budget (R) |  | R 1 500 000 |  |  |  |  |
|  | Number planned & Emergency Maintenance projects undertaken on municipal facilities | 2 | 4 Maintenance Projects done by the 30th June 2020 | 1 Maintenance Projects done | 0 Maintenance Projects were done | The tender for maintenance of facilities still under evaluation/adjudication process | Plan for 2 projects to be completed in Q2 to catch-up with plans |
|  | Budget (R) |  | R2 200 000 |  |  |  |  |
|  | Number of Updated and Approved Indigent Registers | 1 | 1 Updated & Approved Indigent Register by 31 May 2021 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on Eskom Electrification Programme & Projects submitted to Council | 4 | 4 reports on Eskom Electrification Programme & Projects submitted to Council (1 per quarter) | 1 Report on Eskom Electrification Programme & Projects | 1 Report on Eskom Electrification Programme & Projects were submitted to Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Indigent Household (HH) receiving Free Basic Electricity | 6675 HH | 7 500 collections per year 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 5 590 000 |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES AND INFRASTRUCTURE | Number of Reports on the implementation of Water Projects by DWA&S, NMMDM & Sedibeng noted by Council | New | 4 Water Projects Report (1 per quarter) | 1 Water Project Report | 1 Water Project Report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on Waste Removal noted by Council | New | 4 Waste Removal Reports (1 per quarter) | 1 Waste removal Report | 1 Waste removal report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Reports on Housing Projects Implemented by DHS noted by Council | New | 4 Housing Reports (1 per quarter) | 1 Housing Report | 1 Housing Report was noted by Council | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES AND INFRASTRUCTURE | Number of Multi-Purpose centre constructed | 0 | 1 Multi -Purpose centre Constructed to window level by 30 June 2023 (Disaneng MPC Phase 1) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 4 761 250 |  |  |  |  |
|  | Number of Cemeteries Fenced and provided with VIP Toilet | 18 cemeteries fenced | 1 Cemeteries fenced and provided with VIP Toilets (Lokaleng Phase 03) 30 March 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 1 900 000 |  |  |  |  |
|  | Number of Internal Access Road Phase 04 | 25km of road paved | 1 Internal Access Roads completed (120m pf paved roads completed) By 30 June 2023 ( Kraaipan Phase 04) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 2 300 000 |  |  |  |  |
|  | Number rehabilitated Existing Sports Complex | 2 Sports Complex | 1 Rehabilitated Existing Sports Complex Constructed and Completed (Soccer pitch earthworks complete) by 30 June 2023 (Mareetsane Village) | Not a target for this quarter | N/A |  |  |
|  | Budget (R) |  | R 4 750 000 |  |  |  |  |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROVISION OF BASIC MUNICIPAL SERVICES AND INFRASTRUCTURE | Number of Link Roads constructed | 25km of road paved | 1 Link Road constructed in Lokaleng by 30 June 2023 (650m sealed road Phase 03 – Lokaleng to N18) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 5 000 000 |  |  |  |  |
|  | Number of Roads & Storm water constructed | 25km of road paved | 1km Roads & Storm water constructed & completed (Setlhwatlhwe and Ramabesa Phase 02) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 6 000 000 |  |  |  |  |
|  | Number of Sports Facility constructed | 08 Sport Facilities | 1 Sports Facility Constructed by 30 June 2022 – Perimeter Fence, Ablution block and soccer pitch earthworks complete complete (Logageng and Matloding Phase 02) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 6 786 000 |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of Audit Charter & Plan developed & reviewed | 1 | Audit Charter & Plan developed by 31 December 2020 | 1 Audit Charter developed. | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Audit Committee Sittings held | 4 | 4 Audit Committee Sittings held (1 per quarter) | 2 Audit Committee Sittings held | 3 Audit Committee Sittings were held | The over performance was a result of preparation for submission of AFS and Performance information | N/A |
|  | Budget (R) |  | R 200 000 |  |  |  |  |
|  | Number of Internal Audits Conducted | 4 Internal Audits | 4 Internal Audits Conducted (1 per quarter) | 2 Internal Audits Conducted | 2 Internal Audit were conducted | The over performance was a result of preparation for submission of AFS and Performance information | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Internal Audit (IA) Plan Adopted by Audit Committee | 1 | 1 IA Plan developed by 31 May 2020 | Not a target for this | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Risk Management Policies reviewed & adopted | Policy Existing | 1 RMP reviewed & adopted by 31 May 2020 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Internal Audit Reports submitted to Audit Committee for consideration | 4 | 4 Internal Audit Reports submitted to Audit Committee for consideration. (1 per quarter) | 1 Internal Audit Reports submitted | 2 Reports were submitted to Audit Committee | The over performance was as result of submission of AFS and Performance information for submission to AG | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under/over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of revised Risk Management Strategy (RMS) Reviewed and Adopted by Council | Strategy in place | 1 Revised RMS by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Revised Fraud and Corruption Strategy adopted by Council | Strategy in place | 1 Revised Fraud & Corruption Strategy Adopted by Council by 31 May 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE GOOD GOVERNANCE | Number of MPAC Reports submitted to Council for noting | 4 | 4 MPAC Reports submitted to council for noting (1 per quarter) | 1 MPAC Report submitted | 1 MPAC report was submitted | N/A | N/A |
|  | Budget (R) |  | R80 000 |  |  |  |  |
|  | Number of Support Training Conducted for MPAC & Rules Committee | 2 | 2 Support Training Conducted for MPAC & Rules Committee (Q2 & Q4) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | Same as above |  |  |  |  |
| PROMOTE COMMUNITY PARTICIPATION | Number of Ward Committee s Functional | 14 | 14 Functional Ward Committees | 14 Functional Ward Committees | 14 Ward Committees are functional | N/A | N/A |
|  | Budget (R) |  | R2 604 000 |  |  |  |  |
|  | Number of on Ward Committees noted by Council | 4 | 4 Reports on Ward Committees noted by Council | 2 Reports on Ward Committees noted | 1 Report o Ward Committee was submitted | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Ward Committees supplied with Stationery | 2 | 140 Ward Committees supplied with Stationery | 140 Ward Committees supplied with Stationery | 0 Ward Committees were supplied with stationery | The supply chain process was not completed | To be finalized in the Second quarter |
|  | Budget (R) |  | R300 000 |  |  |  |  |
|  | Number of Public Participation Events Supported | 4 | 12 (3 x IDP/Budget/PMS, 3 x Annual Report, 2 x Imbizos & 4 x Ward Comm. Functions) | 1 x Ward Committed Function | 0 Public Participation events were supported | The MPAC schedule was not finalized | The target will be dealt with during the quarter 2 |
|  | Budget (R) |  | R100 000 |  |  |  |  |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives | Performance Indicator | Baseline | Annual Target | Quarter 1 Target | Actual Performance | Reasons for variance (under / over performance) | Corrective measures |
| PROMOTE COMMUNITY PARTICIPATION | Number of Support Initiatives for Traditional Leaders Implemented | 1 | 4 Support Initiatives for Traditional Leaders Implemented | 1 Support Initiative | 1 Support initiative has been implemented | N/A | N/A |
|  | Budget (R) |  | Operational |  |  |  |  |
|  | Number of Dipitso tsa Baagi Held | New | 2 Dipitso tsa Baagi Held (Q3 & Q4) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R50 000 |  |  |  |  |
|  | Number of Youth Summit Held | New | 1 Summit Held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R150 000 |  |  |  |  |
|  | Number of Youth Career Exhibition Held | New | 1 YCE Held by 30 June 2023 | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 50 000 |  |  |  |  |
|  | Number of Youth Development Programmes Held | New | 4 Youth Development programmes held by 30 June 2023 | 1 Youth Development programme held | 1 Youth Development programme was held | N/A | N/A |
|  | Budget (R) |  | R90 000 |  |  |  |  |
|  | Number of Disability Forum Meetings Held | New | 4 Disability Forum Meetings Held (1 per quarter) | 1 Disability Forum Meetings Held | 1 Disability Forum Meetings was Held | N/A | N/A |
|  | Budget (R) |  | R 70 000 |  |  |  |  |
|  | Number of Women’s Forum Meetings Held | 2 | 2 Women’s Forum Meetings Held (2nd and 3rd Quarter) | Not a target for this quarter | N/A | N/A | N/A |
|  | Budget (R) |  | R 70 000 |  |  |  |  |

KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION. Objectives; Performance Indicator; Baseline; Annual Target; Quarter 1 Target; Actual Performance; Reasons for variance (under / over performance); Corrective measures. ENHANCE COMMUNICATION; Number of Communication Strategy Reviewed & Adopted by Council; Strategy in Place; 1 Communication Strategy Reviewed & Adopted by 31 May 2023; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Operational. Number of Reports on Operational Tele Centres; 1; 3 Operational Tele Centres (Tshidilamolomo, Kraaipan & Setlagole); Not a target for this quarter; N/A; N/A; N/A. Budget (R); R 600 000. Number of Reports on Moderations & Assessments; 1; 1 Moderation & Assessment report noted by Council; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Same As Above. Number of Graduation Ceremonies held; 1; 1 Graduation Ceremonies held by 30 June 2023; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Same As Above. Number of Accredited Telecentres; 1; 1 Telecentre Accredited by 30 June 2023; Not a target for this quarter; N/A; N/A; N/A. Budget (R); Same As Above. KPA: SPATIAL RATIONALE. Objectives; Performance Indicator; Baseline; Annual Target; Quarter 1 Target; Actual Performance; Reasons for variance (under / over performance); Corrective measures. IMPROVE SPATIAL PLANNING; Number of General Valuation Rolls implemented; 2012/2017 SDF; 1 General Valuation Roll implemented by 30 June 2023; Advertisement of a tender; Bid Evaluation Committee is yet to sit; N/A; N/A. Budget (R); R1 600 000. Number of Municipal Planning Tribunal appointed; New; 1 MPT appointed by 30 September 2022; MPT appointed; Not Achieved; A resolution by Council was late; The target will be achieved in Quarter 2. Budget (R); Operational. Number of Funding applications submitted for Land Tenure Upgrades; Setlagole & Madibogo; 1 Funding applications submitted for Land Tenure Upgrades by 30 December 2022 (Logageng & Makgobistad); Not a target for this quarter; N/A; N/A; N/A. Budget (R); Operational.