2025/2026

2025/2026

# ratlou local Municipality

TOP LAYER

SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

(SDBIP)

# ratlou local Municipality

TOP LAYER

SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN

(SDBIP)

TABLE OF CONTENTS

TABLE OF CONTENTS

Statement by the Mayor………………………………………………………………………………………………………………………………………..…………………………………………….	2

Overview by the Municipal Manager………………………………………………………………………………………………………………………………………………………………………	3

CHAPTER 1………………………………………………………………………………………….……………………………………………………………………………………………………………..	4

- INTRODUCTION ………………………………………………………………………………………………………………………………………………………………………………………….	4

  - Background……………………………………………………………………………………………………………………….……………………………………………………………….	4

  - Legislative Imperatives ……………………………………………………………………………………………………………………………………………………………………………4

  - Our Approach ………………………………………………………………………………………………………………………………………………………………………………………5

CHAPTER 2…………………………………………………………………………………………………………………………………………….………………………………………………………….	6

- MUNICIPAL BACKGROUND……………………………………………………………………………………………………………..………………………………………………………………	6

  - Brief Muncipal Backgound ……………………………………………………………………………………………………………………………………………………………………..	6

  - Organisational Structure ………………………………………………………………………………………………………………………………………………………………………….6

  - Staffing Information ……………………………………………………………………………………………………………………………..………………………………………………..	7

CHAPTER 3…………………………………………………………………………………………………………………………………………………..…………………………………………………….	8

- 2025/2026 SERVICE DELIVERY OBJECTIVES, KPIs & TARGETS………………………………………………………………………….…………………………………………………………..	8

  - MUNICIPAL STRATEGY MAP ………………………………………………………………………………………………………………………………………………………………………9

  - KEY PERFORMANCE INDICATORS AND QUARTERLY TARGETS………………………………………………………..…………………………………………………………………….10

Municipal Transformation and Institutional Development…………………………………………………..…………………………………………………………………….	10

Financial Viability …………………………………………………………………………………………………….……………………………………………………………………	16

Local Economic Development ………………………………………………………………………………………………………………………………………………………..	18

Infrastructure Development and Service Delivery …………………………………………………………………………………………………………………………………	20

Good Governance and Public Participation ………………………………………………………………………………………………………………………………………	23

Spatial Rationale ………………………………………………………………………………………………………………………………………………………………………….	26

CHAPTER 4 ..................................................................................................................................................................................................................................................................................	27

- MUNICIPAL FINANCIAL INFORMATION ……………………………………………………………………………………………………………………………………………………………….	27

  - CAPITAL PROJECTS MONTHLY EXPENDITURE PROJECTIONS ………………………………………………………………………………………………………………………………	29

STATEMENT BY THE MAYOR

The SDBIP provides the vital link between the mayor, council (executive) and the administration, and facilitates the process for holding management accountable for its performance. The SDBIP is a management, implementation and monitoring tool that will assist the mayor, councillors, municipal manager, senior managers and community. It is the intention of the Ratlou Local Municipality to formulate a well-informed SDBIP in order to ensure that appropriate information is circulated internally and externally for purposes of monitoring the execution of the budget, performance of senior management and achievement of the strategic goals of the municipality as set out in the Integrated Development Plan.

It will ensure that the Administrative Head (Municipal Manager) is able to monitor the performance of senior managers, the Mayor, in turn, to monitor the performance of the municipal manager and more importantly, it will ensure that the community is able to monitor the performance of the municipality. In order to achieve this, the SDBIP should therefore determine the performance agreements between the Mayor and the Municipal Manager and, again in turn, between the Municipal Manager and senior managers (Strategic Managers) formulated and signed at the start of every financial year and approved by the mayor.

________________

Cllr M. JAFTA

HONOURABLE MAYOR

DATE_____/_____/______

OVERVIEW BY THE MUNICIPAL MANAGER

The development, implementation and monitoring of a Service Delivery and Budget Implementation Plan (SDBIP) is a requirement of the Municipal Finance Management Act, (MFMA) (Act No. 56 of 2003).

The SDBIP is the management and implementation tool which sets in-year information, e.g. quarterly service delivery and monthly budget targets, and links each service delivery output to the budget of the Municipality. It provides credible management information and a detailed plan how the Municipality will provide services, and which inputs and financial resources should be used.

It is the mechanism that ensures that the IDP and Budget are aligned. It is an expression of the objectives of the municipality in quantifiable outcomes that will be implemented by the administration for the financial period. It includes the service delivery targets and performance indicators for each quarter, which is linked to the performance agreements of senior management. It therefore facilitates oversight over financial and nonfinancial performance of the municipality.

The SDBIP also assists the executive, council and the community in their respective oversight responsibilities since it serves as an implementation and monitoring tool

I thank you

_________________

LLOYD LEOKO

MUNICIPAL MANAGER

# CHAPTER 1

# INTRODUCTION

  - Background

The Service Delivery and Budget Implementation Plan represent the operationalization of the Integrated Development Plan which was tabled in council as council’s strategic document. The Service Delivery and Budget Implementation Plan cascades the IDP Priorities, Objectives, and Targets into a one-year plan through which council will hold the administration accountable.

The SDBIP therefore serves as a “contract” between the administration, council and community expressing the goals and objectives set by the council as quantifiable outcomes that can be implemented by the administration over the next twelve months. This provides the basis for measuring performance in service delivery against end of-year targets and implementing the budget. (MFMA Circular 13, 2005, pg2)

  - Legislative Imperative

In terms of Section 53 (1) (c) (ii) of the Local Government: Municipal Finance Management Act (MFMA), the SDBIP is defined as a detailed plan approved by the mayor of a municipality for implementing the municipality’s delivery of municipal services and its annual budget, and which must indicate the following: –

- projections for each month of –

  - revenue to be collected, by source; and

  - operational and capital expenditure, by vote

- service delivery targets and performance indicators for each quarter, and

- other matters prescribed

According to Section 53 of the MFMA, the Mayor is expected to approve the SDBIP within 28 days after the approval of the budget. In addition, the Mayor must ensure that the revenue and expenditure projections for each month as well as the service delivery targets and performance indicators as set out in the SDBIP are made public after approval.

The National Treasury, MFMA Circular 13 further provides a guide on the format and contents of the service delivery and budget implementation plan. According to Circular 13, the Top Layer SDBIP must consist of the following main sections:

- Monthly projections of revenue to be collected for each source

- Monthly projections of expenditure (operating and capital) and revenue for each vote

- Quarterly projections of service delivery targets and performance indicators for each vote

- Ward information for expenditure and service delivery

- Detailed capital works plan broken down by ward over three years

Circular 13 also introduce technical service delivery and budget implementation plans, (technical SDBIPs) which cascade the Top Layer SDBIP into departmental plans.

  - Our Approach

This plan attempts to comply with the requirements of the MFMA and Circular 13. It provides the strategic link between the IDP, budget and the operational plan of the municipality for a period of 12 months as required by legislation.

The quarterly targets captured here will only indicate the number of outputs or indicators per quarter and the last date in terms of quarter in which the target must be achieved. Where there is a need to maintain a standard, the quarterly target will be captured as 100% meaning the annual target must be maintained.

# CHAPTER 2

# MUNICIPAL BACKGROUND

  - Brief Municipal Background

Ratlou Local Municipality is one of the five local municipalities under the jurisdiction of Ngaka Modiri Molema District Municipality in the North-West Province. The municipality is a category B, and was established in 2000.

It is divided into 14 wards and has 140 ward committee members. It is predominantly rural in character and agriculture forms the dominant economic activity. The municipality is led by a council of 27 elected councillors. The Mayor is the chairperson of the Executive Committee which is comprised of senior councillors who serve as chairpersons of the municipality’s portfolio committees.

  - Institutional Arrangement

The municipality has 6 departments including the Office of the Municipal Manager. The departments are led by the Acting Municipal Manager and Senior Manager/Acting Senior Managers as indicated in the figure below.

## Office of the Municipal Manager

- Department of Corporate Services

- Department of Technical Services

- Department of Town Planning & Development

- Department of Budget & Treasury

- Department of Community Services

  - Staffing Information

The municipality is led by the Acting Municipal Manager and 5 Senior Manager/Acting Senior Managers;

The municipality has an estimated staff compliment of about 235 employees. Some of the employees are unionised through IMATU and SAMWU

CHAPTER 3

# 2025/2026 SERVICE DELIVERY OBJECTIVES, KEY PERFORMANCE INDICATORS AND TARGETS

The section that follows contains the municipal service delivery objectives, Key Performance Indicators and targets for the 2025/2026 financial year.

The first part contains council’s high-level objectives, which indicate what the municipality hope to deliver at the end of the financial year and how the organisation will look like to both the external and internal customers.

Ratlou Local Municipality utilises the Balanced Score Card as the model to plan, implement, monitor and evaluate performance. With an emphasis on "balanced", the Scorecard uses four perspectives to answer critical service delivery questions. This provides the balance that successful organizations seek in measuring performance: The perspectives of the balanced Score Card are depicted in the table below:

| Perspective | Definition | Leading Question |
| --- | --- | --- |
| Customer | The municipality must focus on how to meet service needs in an efficient manner | Is the organization delivering the services communities or its customers want? |
| Financial | The municipality must focus on how to meet service needs in an efficient manner. | Is the service delivered at a good price? |
| Internal Business | The municipality needs to focus on those critical operations that enable them to satisfy citizens. | Can the organisation improve upon a service by changing the way a service is delivered? |
| Innovation, Learning and Growth | The organization’s ability to improve and meet citizen demands ties directly to the employees’ ability to meet those demands | Is the organisation maintaining technology and employee training for continuous improvement? |

The high level municipal strategic objectives are contained in the table below according to the perspectives of the Balanced Score Card and the National Key Performance Areas of Local Government.

## 3.1	Municipal Strategy Map

| Key Performance Area | Municipal Transformation and Organisational Development | Service Delivery and Infrastructure Development | Local Economic Development | Municipal Financial Viability | Good Governance and Public Participation | Spatial Rationale |
| --- | --- | --- | --- | --- | --- | --- |
| CUSTOMER |  | Provision of Basic Municipal Services and Infrastructure |  |  | Enhance Communication |  |
|  |  |  | Promote Local Economic Development & Job Creation |  |  |  |
|  |  | Facilitate the Provision of Housing Services |  |  | Promote Community Participation |  |
|  |  |  |  |  | Promote Good Governance |  |
| FINANCIAL |  |  |  | Improve Asset Management |  |  |
|  |  |  |  | Enhance Revenue |  |  |
|  |  |  |  |  | Promote Financial Accountability |  |
| INNOVATION LEARNING AND GROWTH | Retain and Recruit Talented Employees |  |  |  |  |  |
|  | Achieve Employment Equity |  |  |  | Promote Accountable, Efficient and Transparent Organization |  |
|  | Promote Innovation Learning and Growth |  |  |  |  |  |
| INTERNAL BUSINESS | Achieve a Positive & Productive Employee Climate |  |  |  | Achieve Clean Audit | Improve Spatial Planning |
|  | Improve Technology Efficiency |  |  |  |  |  |
|  | Promote Planning and Performance Management |  |  |  |  |  |

## 3.2	Key Performance Indicators and Quarterly Targets

| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Planning and Performance Management | Number of reviewed IDP Adopted by Council | 2022/2027 IDP | 1 2026/2027 IDP Adopted by Council by 31 May 2026 | R 50 000 | Integrated Planning | - | - | Project Phase Draft IDP Approved by 31st March 2026 | Community Consultation & Adopted 26/27 IDP by 31 May 2026 | Council Resolution & IDP Document |
|  | Number of SDBIP Approved by the Mayor | 2017/2022 IDP | 1 Service Delivery and Budget Implementation Plan Approved by 12 June 2026 |  |  | - | - | - | 1 Service Delivery and Budget Implementation Plan Approved by 12 June 2026 by the Mayor | Copy of SDBIP signed by the mayor |
|  | Number of IDP Rep forums held | 3 | 4 IDP Representative forum meetings held by 30 June 2026 (1 per quarter) | Operational |  | 1 IDP Representative forum meetings held by 30 September 2025 | 1 IDP Representative forum meetings held by 30 December 2025 | 1 IDP Representative forum meetings held by 30 March 2026 | 1 IDP Representative forum meetings held by 30 June 2026 | Attendance Registers, Agenda, Minutes & Invite |
|  | Number of IDP Steering Committee meetings held | 3 | 4 IDP Steering Committee Meetings held by 30 June 2026(1 per quarter) | Operational |  | 1 IDP Steering Committee Meeting held by30 September 2025 | 1 IDP Steering Committee Meeting held by 30 December 2025 | 1 IDP Steering Committee Meeting held by 30 March 2026 | 1 IDP Steering Committee Meeting held by 30 June 2026 | Attendance Registers, Agenda, Minutes & Invite |
|  | Number of Community meetings held | 1 | - Community meetings held by 30 June 2026 (Q 2 & Q 4) | Operational |  | - | 1 Community Meeting held by 31 Dec 2025 | - | 1 Community Meeting held by 30 June 2026 | Attendance Registers, Agenda & Invite |
|  | Number of IDP & Budget Schedule Activities adopted by Council | 2017/2022 Schedule of Activities (IDP/Budget) | 1 2025/2026 IDP & Budget Schedule of Activities Adopted by 31 August 2025 | Operational |  | IDP & Budget Schedule of Activities Adopted by 31 August 2025 | - | - | - | Council Resolution |
|  | Number of Mid-term Assessment Held | 1 | 1 Mid Term Assessment held by 31 January 2026 | R 600 000 |  | - | - | 1 Mid Term Assessment held by 31 January 2026 | - | Report signed off by MM |

| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Planning and Performance Management | Number of Strategic Planning sessions held | 2024/2025 | 1 Strategic Planning Session held by 31 December 2025 | R 600 000 | Integrated Planning | - | -1 Strategic Planning Session held by 31 December 2025 |  | - | Council Resolution & Strategic Planning Report |
|  | Number 2024/25 Annual Reports adopted by council | 2023/2024 Annual Report | 1 24/25 Annual Report Adopted by Council by 31 January 2026 | R 210 000 |  | - | - | 24/25 Annual Report Adopted by Council by 31 January 2026 | - | Council Resolution Annual report |
|  | PMS Policies reviewed & adopted by Council | Existing | 1 PMS Policy reviewed & adopted by Council by 31 May 2026 | Operational |  | - | - | - | 1 PMS Po licy reviewed & adopted by Council by 31 May 2026 | Council Resolution PMS Policy |
| Improve Technology Efficiency | Number of reviewed and adopted IT Master Plans | Existing | 1 IT Master Plan reviewed & adopted by Council by 30 June 2026 | R 800 000 | Technology Efficiency | .- | - | - | 1 IT Master Plan reviewed & adopted by Council by 30 June 2026 | Council Resolution on the Report IT Master Plan |
|  | Number of software licences renewed | 4 | 3 software licences renewed by 30 July 2025 (Teammate Payday, CaseWare, Pastel & Office) | R 900 000 |  | 3 software licences renewed by 30 July 2025 (Pastel, Teammate, CaseWare Office & Payday) | - | - | - | Signed Report by MM |
|  | Number of Reports on Software and Hardware updated | Existing | 4 Reports on Software & Hardware updates by 30 June 2026 (1 per quarter) | R 590 000 |  | 1 Report on Software & Hardware updates by 30 September 2025 | 1 Report on Software & Hardware updates by 31 Dec 2025 | 1 Report on Software & Hardware updates by 30 March 2026 | 1 Report on Software & Hardware updates by 30 June 2026 | Signed Report by MM |
|  | Number of Operational Disaster and Business Continuity Plans Implemented | Existing | 1 Operational Disaster and Business Continuity Plan implemented by 30 June 2026 | R 150 000 |  | - | - | - | 1 Operational Disaster and Business Continuity Plan implemented by 30 June 2026 | Signed Report by MM ODBCP |

| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Retain & Recruit Talented Employees | Number of Revised Policies adopted by Council | 28 Policies | 31 HR Policies reviewed & adopted by 30 May 2026 | Operational | Talented Employees | - | - | - | 31 HR Policies reviewed & adopted by 30 May 2026 | Council Resolution & 31 Adopted HR Policies |
|  | Number of Human Resource Management Strategy Developed & Reviewed | Existing | 1 Human Resource Management Strategy Developed & Reviewed by 30 May 2026 | Operational |  | - | - | - | 1 Human Resource Development Strategy Developed & Reviewed - by 30 May 2026 | Council resolution Human Resources Management Strategy |
| Promote Innovation Learning and Growth | Number of 2025/2026 Workplace Skills Development Plan (WSDP) Developed & Adopted by Council | 2024/2025 WSDP | 1 WSDP adopted by 31 March 2026 | R 800 000 | Skilled Workforce & Community | - | - | - | 1 2025/2026 WSDP submitted to LGSETA by 30th April 2025 | Council Resolution & WSDP |
|  | Number of 2025/2026 WSDP submitted to LGSETA by 30th April 2025 |  | 1 2025/2026 WSDP submitted to LGSETA by 30th April 2025 | Operational |  | - | - | - | 1 WSDP adopted by 30 May 2026 | Proof of Submission & 2025/2026 WSDP |
|  | Number of Municipal Employees benefitting from Bursary Policy | New | 08 Municipal Employees benefitting from Bursary Policy by 30 June 2026 | R 350 000 |  | - | - | - | 08 Municipal Employees benefitting from Bursary Policy by 30 June 2026 | Signed Agreements |
|  | Number of applicants benefiting from the Tertiary fund assistance | 28 | 28 applicants benefiting from the Tertiary fund assistance by 30 March 2026 | R 600 000 |  | - | - | 28 applicants benefiting from the Tertiary fund assistance by 30 March 2026 | - | Signed Agreements |

| KPA: MUNICIPAL TRANSFORMATION & INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Achieve Positive Employee Climate | Number Employment Equity Plans submitted to the dept of employment & labour | Employment Equity Plan | 1 Employment Equity plan submitted to the Department of Employment & Labour by 15 January 2026 | Operational | Representative workforce | - | - | 1 Employment Equity plan submitted to the Department of Employment & Labour by 15 January 2026 | - | Council resolution and acknowledgement letter from Dept. Labour |
|  | Number of LLF Meetings held | 3 | 4 LLF Meetings held by 30 June 2026 | Operational |  | 1 LLF Meeting held by 30 Sep 2025 | 1 LLF Meeting held by 31 Dec 2025 | 1 LLF Meeting held by 30 March 2026 | 1 LLF Meeting held by 30 June 2026 | Invitations, Minutes, Attendance Register & Agenda |
|  | Number of employees that have signed Code of conduct | 215 | 212 employees that have signed Code of conduct by 31 July 2025 | Operational |  | 212 employees that have signed Code of conduct by 31 July 2025 | - | - | - | Signed copies of Code of Conduct |
|  | Number of EAP & OHS programmes implemented | 3 | - EAP & OHS programmes implemented by 30 June 2026 ( Q1 & Q4) | R 450 000 |  | 1 EAP and OHS programme implemented by 30 September 2025 | - | - | 1 EAP and OHS programme implemented by 30June 2026 | Council Minutes, Reports on Implementation of EAP & OHS programme |

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Financial Accountability | 2026/2027 Budget approved by Council | 2024/2025 Budget | 2026/2027 Budget approved by 31 May 2026 | Operational | Accountable and Transparent Institution | Budget Schedule of Activities Adopted by 28 Aug 2025 | - | Draft Budget by 30 March 2026 | 2026/2027 Budget Approved by 31 May 2026 | Council Resolution & Approved Budget |
|  | Number of Budget Related policies* adopted by Council | 14 Policies | 16 Budget related Policies Adopted by 30 May 2026 | Operational |  | - | - | 16 Draft Policies Noted by Council by 30 March 2026 | 16 Policies Adopted by Council by 31 May 2026 | Council Resolution & Policies |
|  | 2025/2026 Adjustment Budget Approved by Council | 2024/25 Adjustment budget approved | 1 Approved 2025/2026 Adjustment Budget by 28 February 2026 | Operational |  | - | Budget Analysis Report (Actuals) by 31 December 2025 | 1 Approved 2025/2026 Adjustment Budget by 28 February 2026 | - | Council Resolution & Approved 2025/2026 Adjustment Budget |
|  | Number of Council approved 2025/2026 Annual Financial Statements (AFS) submitted to the Office of the Auditor-General (A-G) | 2023/2024 Audited AFS | 1 2025/2026 AFS submitted to A-G by 30 August 2026 | R 7 500 000 |  | 1 2025/2026 AFS submitted to A-G by 30 August 2026 | - | - | - | Acknowledgement letter by the Office of A-G/ Proof of Submission of AFS |
|  | Number of Supply Chain Management reports submitted to council | Existing | 4 Supply Chain Management reports submitted to council for noting by 30 June 2026 (1 per quarter) | Operational |  | 1 Supply Chain Management report submitted to Council for noting by 30 Sep 2025 | 1 Supply Chain Management report submitted to Council for noting by 31 Dec 2025 | 1 Supply Chain Management report submitted to Council for noting by 30 March 2026 | 1 Supply Chain Management report submitted to Council for noting by 30 June 2026 | Council Minutes & Supply Chain Management Reports |

* Policies:  Approval of Budget Policy, Funding & Reserve Policy, Credit Control & Debt Collection Policy, Cash Management & Investment, Assets Policy, Indigent Support, Virement Policy, Provision for Bad Debt Policy,  Tariff Policy, Supply Chain Management Policy, Overtime Policy, Cellphone Policy, Subsistence and Travelling, Leave Polic, Bursary Policy & Rates Policy

| KPA: FINANCIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline |  | Annual Target |  | Budget | Outcome Indicator | Quarterly Targets |  |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  |  |  | Quarter 1 |  | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Revenue Enhancement | Number of Consumer Awareness campaigns held | New |  | 2 Consumer Awareness campaigns held by 30 June 2026 |  | Operational | Increased Municipal Revenue | 1 Consumer Awareness campaigns held by 30 September 2025 |  | - | 1 Consumer Awareness campaigns held by 30 March 2026 | - | Attendance Register, Agenda, Minutes & Invite |
|  | Number of MPRA meetings held | Existing |  | 4 MPRA meetings held by 30 June 2026 (1 per quarter) |  | Operational |  | 1 MPRA meetings held by 30 September 2025 |  | 1 MPRA meetings held by 31 December 2025 | 1 MPRA meetings held by 30 March 2026 | 1 MPRA meetings held by 30 June 2026 | Attendance Register, Agenda, Minutes & Invite |
|  | % Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) | 35% |  | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) by 30 June 2026 |  | Operational |  | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) by 30 Sept 2025 |  | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) by 31 Dec 2025 | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) by 30 March 2026 | 95% Collection of billed revenue (i.e., Opening Balance + Billing-impairment-closing + billing*100) by 30 June 2026 | Sec 71 Report |
| Improve Assets Management | Number of Reports on Updated Assets Register noted by the Audit Committee | Existing |  | 4 Reports on Updated Assets Registers noted by the Audit Committee by 30 June 2026 |  | Operational | Improved Assets | 1 Report on Updated Assets Registers noted by the Audit Committee by 30 Sept 2025 |  | Report on Updated Assets Registers noted by the Audit Committee by 31 Dec 2025 | Reports on Updated Assets Registers noted by the Audit Committee by 30 March 2026 | Report on Updated Assets Registers noted by the Audit Committee by 30 June 2026 | Committee Minutes & Updated Assets Registers |
|  | Number of Assets committees established | Existing |  | 1 Asset committees established by 30 Sept 2025 |  | Operational |  | 1 Asset committees established by 30 Sept 2025 |  | - | - | - | Appointment Letters |
|  | Number of Assets Verifications conducted | Existing |  | 4 Assets Verifications conducted by 30 June 2026 |  | Operational |  | 1 Assets Verifications conducted by 30 September 2025 |  | Assets Verifications conducted by 31 December 2025 | Assets Verifications conducted by 30 March 2026 | Assets Verifications conducted by 30 June 2026 | Assets Verification Report |
|  | Number of reports on Fleet Usage submitted to Council | 15 |  | 4 reports on Fleet Usage submitted to Council by 30 June 2026 (1 per quarter) |  | R 4 870 000 |  | 1 report on Fleet Usage submitted to Council by 30 September 2025 |  | 1 report on Fleet Usage submitted to Council by 31 December 2025 | 1 report on Fleet Usage submitted to Council by 30 March 2026 | 1 report on Fleet Usage submitted to Council by 30 June 2026 | Council Minutes, Reports on Fleet Usage |
|  | Number of Assets Committee Meetings held | 3 |  | 3 Assets Committee Meetings held by 30 June 2026 |  | Operational |  | - |  | 1 Asset Committee Meeting held by 31 December 2025 | 1 Asset Committee Meeting held by 30 March 2026 | 1 Asset Committee Meeting held by 30 June 2026 | Attendance Registers |
| KPA: FINICIAL VIABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Corporate Objective |  | Key Performance Indicator | Baseline | Annual Target |  | Budget |  | Outcome Indicator |  | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Achieve Clean Audit |  | Number of quarterly AFS submitted to Council | New | 3 quarterly AFS submitted to Council for noting by 30 June 2026 (1 per quarter) |  | Operational |  | Improved Audit Outcome |  |  | 1 quarterly AFS submitted to Council for noting by 31 December 2025 | 1 quarterly AFS submitted to Council for noting by 30 March 2026 | 1 quarterly AFS submitted to Council for noting by 30 June 2026 | Council Minutes & AFS |
|  |  | Number of Audit Plans Developed to address Auditor – General (A-G Queries adopted by Council | 2021/22 Audit Action Plan | 1 Audit Action Plan Developed by 31 January 2025 |  | Operational |  |  |  | - | - | 1 Audit Action Plan Developed by 31 January 2025 | - | Proof of Submission/Acknowledgment letters from PT and NT |
|  |  | Number of Reports on the Implementation of the Audit Action Plan noted by Council | Existing | 2 Reports on the Implementation of the Audit Action Plan noted by Council by 30 June 2026 (3rd and 4th Quarter ) |  | Operational |  |  |  | - | - | 1 report on the implementation of the AAP noted by Council by 30 March 2026 | 1 report on the implementation of the AAP noted by Council by 30 June 2026 | Plan Signed by Municipal Manager & Reports on the implementation of PAAP, Council Munites |
|  |  | Number of PAAP reports included in the Management Meeting | PAAP Progress Report | 4 PAAP reports included in the Management Meeting (1 per quarter) 30 June 2026 |  | Operational |  |  |  | 1 PAAP report included in the Management Meeting by 30 September 2025 | 1 PAAP report included in the Management Meeting by 31 December 2025 | 1 PAAP report included in the Management Meeting by 30 March 2026 | 1 PAAP report included in the Management Meeting by 30 June 2026 | Management Minutes & PAAP Reports |
|  |  | Number of Procurement Plans developed and adopted by Council | Existing | 1 Procurement Plan developed and adopted by Council by 31 July 2025 |  | Operational |  |  |  | 1 Procurement Plan developed and adopted by Council by 31 July 2025 | - | - | - | Council Resolution & Adopted Procurement Plan |

| KPA: LOCAL ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Local Economic Development & Job Creation | Number of Jobs created through Expanded Public Works Programme, Community Workers Programme, Capital Projects and other Local Economic Development initiatives | 1000 | 1769 Jobs created by 30 June 2026 | R 33 906 450 (MIG) | Growing Local Economy & Improved Livelihoods | - | - | - | 1769 Jobs created by 30 June 2026 | Signed List of Beneficiaries & Employment Contracts |
|  |  |  |  | R 2 000 000 (EPWP) |  |  |  |  |  |  |
|  | Number of SMMEs/Cooperatives support initiatives | 4 | 6 SMMEs/Cooperatives support initiatives by 30 June 2026 (Funding, Business Plan Development, Exhibitions, Training & Workshops) | R650 000 |  | - | 2 SMMEs/Cooperatives Support initiatives by 31 December 2025 | 2 SMMEs/Cooperatives Support initiative by 30 March 2026 | 2 SMMEs/Cooperatives Support initiatives by 30 June 2026 | Council minutes, Report on SMME/Cooperatives Support Initiatives |
|  | Number of reports on the implementation of the SLP | Existing | 4 reports on the implementation of the SLP by 30 June 2026 (1 per quarter) | Operational |  | 1 report on the implementation of the SLP by 30 September 2025 | 1 report on the implementation of the SLP by 31 December 2025 | 1 report on the implementation of the SLP by 30 March 2026 | 1 report on the implementation of the SLP by 30 June 2026 | Council Minutes & Report on SLP |
|  | Number of Signage & Branding Erected (Information Boards) | New | 10 Signage & Branding Erected by 30 June 2026 (Information Boards) | R150 000 |  | - | - | - | 10 Signage & Branding Erected | Proof of Installation (Photos & Report) |
|  | Number of reports on Profiled Lodges, Game Lodges & B&Bs | New | 3 Reports on Profiled Lodges, Game Lodges & B&Bs noted by Council by 31 December 2025 | Operational |  | 1 Report on Profiled Lodges, Game Lodges & B&Bs noted by Council by 30 September 2025 | 2 Reports on Profiled Lodges, Game Lodges & B&Bs noted by Council by 31 December 2025 | - | - | Council Minutes & Report on profiled lodges |

| ### KPA: SPATIAL RATIONALE |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Improve Spatial Planning | Number of reports on Land Use Applications noted by Council | 2020/2025 SDF | 4 reports on Land Use Applications submitted to Council for Noting by 30 June 2026 (1 per quarter) | Operational | Integrated Sustainable Human Settlement | 1 report on Land Use Applications submitted to Council for Noting by 30 September 2025 | 1 report on Land Use Applications submitted to Council for Noting by 31 December 2025 | 1 report on Land Use Applications submitted to Council for Noting by 30 March 2026 | 1 report on Land Use Applications submitted to Council for Noting by 30 June 2026 | Council Minutes & Copies of Approved Reports |
|  | Number of Site Demarcations conducted | New | 500 Site Demarcations conducted by 30 June 2026 | R 2 000 000 |  | - | - | - | 500 Site Demarcations conducted by 30 June 2026 | Appointment Letters, & Reports |
|  | Number of reviewed & adopted land use schemes adopted by Council | 2016 Land Use Scheme | 1 Reviewed and adopted Land Use Scheme by 30 June 2026 | R 150 000 |  | - | - | - | 1 reviewed and adopted land use scheme by 30 June 2026 | Council Minutes. Copy of Land Use Scheme & Reports |
|  | Number of reports on the Re-Development of Setlagole Commercial Hub | Complex existing | 4 Reports on the Re-Development of Setlagole Commercial Hub noted by Council (1 Per quarter) | R 150 000 |  | 1 report on the Setlagole Re-Development noted by Council by 30 September 2025 | 1 report on the Setlagole Re-Development noted by Council by 31 December 2025 | 1 report on the Setlagole Re-Development noted by Council by 30 March 2026 | 1 report on the Setlagole Re-Development noted by Council by 30 June 2026 | Council Minutes & Report on the Re-Development of Setlagole Commercial Hub |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Provision of Basic Municipal Services and Infrastructure | Number of Reports on Waste Removal noted by Council | New | 4 Waste Removal Reports noted by Council by 30 June 2026 (1 per quarter) | Operational | Clean & Healthy Environment | 1 Waste removal Report noted by Council by 30 September 2025 | 1 Waste removal Report noted by Council by 31 December 2025 | 1 Waste removal Report noted by Council by 30 March 2026 | 1 Waste removal Report noted by Council by 30 June 2026 | Council Minutes & Reports on Waste Removal |
|  | Number of Disaster Committees established | New | 1 Disaster Committee established by 30 September 2025 | Operational |  | 1 Disaster Committee established by 30 September 2025 | - | - | -- | Attendance Register, Copies of Acceptance letters by Committee Members |
|  | Number of Disaster Management Committee Meetings held | 4 | 3 Disaster Committee meetings held by 30 June 2026 | Operational |  | - | 1 Disaster Committee meetings held by 31 December 2025 | 1 Disaster Committee meetings held by 30 March 2026 | 1 Disaster Committee meetings held by 30 June 2026 | Attendance Register, Invite, Minutes & Agenda |
|  | Number of Traffic Sites with operational drivers’ license testing Grounds established | New | 1 Traffic Sites with operational drivers’ license testing Grounds established by 30 June 2026 | R 3 000 000 |  | - | - | - | 1 Traffic Sites with operational drivers’ license testing Grounds established by 30 June 2026 | Completion Certificate |
|  | Number of reports on Road and Public safety awareness campaigns held | New | 4 Reports on Road and Public safety awareness campaigns held by 30 June 2026 | Operational |  | 1 Report on Road and Public safety awareness campaigns held by30 September 2025 | 1 Report on Road and Public safety awareness campaigns held by31 December 2025 | 1Report on Road and Public safety awareness campaigns held by 30 March 2026 | 1 Report on Road and Public safety awareness campaigns held by 30 June 2026 | Attendance Register, Invites & report on Road and Public safety awareness |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Innovation, Learning & Growth | Number of Library Awareness Programmes Held | 4 | 5 Library Awareness Programmes Held by 30 June 2026 | Operational | Clean & Healthy Environment Improved Livelihoods & Better Community Services | 1 Library Awareness programme held by 30 Sep 2025 | 2 Library Awareness programme held by 31 Dec 2025 | 1 Library Awareness programme held by 30 March 2026 | 1 Library Awareness programme held by 30 June 2026 | Report to Council on Library awareness programme, Invite & Attendance Register |
|  | Number of Library Statistical Reports submitted to ACSR | New | 4 Library Statistical Reports submitted to ACSR by 30 June 2026 | Operational |  | 1 Library Statistical Report submitted to ACSR by 30 September 2025 | 1 Library Statistical Report submitted to ACSR by 31 Dec 2025 | 1 Library Statistical Report submitted to ACSR by 30 March 2026 | 1 Library Statistical Report submitted to ACSR by 30 June 2026 | Report to Council on Library Statistics & Proof of Submission |
|  | Number of Libraries with Functional Committees | New | 3 Libraries with Functional Committees by 30 June 2026 (Q2, Q3&Q4) | Operational |  | - | 1 Library with Functional Committee by 31 Dec 2025 | 1 Library with Functional Committee by 30 March 2026 | 1 Library with Functional Committee by 30 June 2026 | Report to Council on Functionality of Library Committees |
|  | Number of Library Committee Meeting Held | New | 12 Library Committees meetings held by 30 June 2026 (1 per Quarter) | Operational |  | 3 Library Committee meeting held by 30 September 2025 | 3 Library Committee meeting held by 31 Dec 2025 | 3 Library Committee meeting held by 30 March 2026 | 3 Library Committee meeting held by 30 June 2026 | Report to Council, Agenda, Invite & Minutes, Attendance Register |
|  | Number of New Library Users registered | New | 60 New Library users registered by 30 June 2026 | Operational |  | 15 New Library users registered by 30 September 2025 | 15 New Library users registered by 31 Dec 2025 | 15 New Library users registered by 30 March 2026 | 15 New Library users registered by 30 June 2026 | Report to Council & register of New Users |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Provision of Basic Municipal Services and Infrastructure | Number of Reports on Serviced and Maintained High Mast & Flood Lights | 4 Reports | 4 Reports on Serviced and Maintained High Mast & Flood Lights by 30 June 2026 | R 2 500 000 | Improved Livelihoods Better community services | 1 Report on Serviced and Maintained High Mast & Flood Lights by 30 Sep 2025 | 1 Report on Serviced and Maintained High Mast & Flood Lights by 31 Dec 2025 | 1 Report on Serviced and Maintained High Mast & Flood Lights by 30 March 2026 | 1 Report on Serviced and Maintained High Mast & Flood Lights by 30 June 2026 | Technical Report on serviced high mast lights signed by Senior Manager |
|  | Number planned Maintenance projects undertaken on municipal facilities | 2 | 5 Planned Maintenance projects undertaken on municipal facilities by the 30th June 2026 | R 3000 000 |  | 1 Maintenance Projects done by 30 Sep 2025 | 1 Maintenance Projects done by 31 Dec 2025 | 1 Maintenance Projects done by 30 March 2026 | 1 Maintenance Projects done by 30 June 2026 | Complete project Files with Completion Certs |
|  | Number of Updated and Approved Indigent Registers | 1 | 1 Updated & Approved Indigent Register by 31 May 2026 | Operational |  | - | - | - | 1 Updated & Approved Indigent Register by 31 May 2026 | Council Resolution Updated and adopted Indigent Register |
|  | Number of Reports on Eskom Electrification Programme & Projects submitted to Council | 4 | 4 reports on Eskom Electrification Programme & Projects submitted to Council by 30 June 2026 (1 per quarter) | Operational | Clean & Healthy Environment | 1 Report Eskom Electrification Programme & Projects submitted to Council by 30 Sept 2025 | 1 Report Eskom Electrification Programme & Projects submitted to Council by 31 Dec 2025 | 1 Report Eskom Electrification Programme & Projects submitted to Council by 30 March 2026 | 1 Report Eskom Electrification Programme & Projects submitted to Council by 30 June 2026 | Council Minutes Reports on Eskom Electrification |

| KPA: INFRASTRUCTURE DEVELOPMENT AND BASIC SERVICE DELIVERY |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Provision of Basic Municipal Services and Infrastructure | Number of High Mast Lights supplied, Delivered, energised and installed in Ward 06 | 230 | 10 High Mast Lights supplied, Delivered, installed & energised by 31 December 2025 | R 3 213 150.96 | Clean & Healthy Environment | 10 foundations constructed by 30 Sept 2025 | 10 High Mast Lights supplied, Delivered and installed by 31 December 2025 | - | - | Completion Certificate |
|  | Number of Internal access roads constructed | 1km | 1 km Internal Access roads base layer completed by 30 June 2026 (Setlhwatlhwe) | R 5 002 937.37 |  | Site establishment complete and work commenced by 30 Sept 2025 | Roadbed complete for 1 km by 31 Dec 2025 | Sub-base complete for 1km by 30 Mar 2026 | Base layer complete for 1 km by 30 June 2026 | Progress report |
|  | Number of Internal access roads constructed | 5km | 0.8 Internal Access Road Base Layer completed by Council by 30 June 2026 (Kraaipan) | R 3 678 918.92 |  | Site establishment complete and work commenced by 30 Sept 2025 | Roadbed complete for 0.8 km by 31 Dec 2025 | Sub-base complete for 0.8km by 30 Mar 2026 | Base layer complete for 0.8 km by 30 June 2026 | Progress report |
|  | Number of Internal access roads constructed | 3.1km | 3.5km Internal Access roads constructed by Council by 30 June 2026 (Setlagole) | R 5 361 380.30 |  | Site establishment complete and work commenced by 30 Sept 2025 | Roadbed complete for 1 km by 31 Dec 2025 | Sub-base complete for 1km by 30 Mar 2026 | Base layer complete for 1 km by 30 June 2026 | Progress report |
|  | Construction Gareleng Community Hall | New | 1 Community Hall constructed by 30 Sept 2025 | R 954 833.64 |  | 1Community Hall complete and handed over to the community by 30 Sept 2025 | - | - | - | Completion Certificate |
|  | Number of Cemetries fenced | 4 | 1 Cemetery fenced with concrete palisade and handed to the community by 30 Sept 2025 | R 467 612.65 |  | 1 Cemetery fenced with concrete palisade and handed to the community by 30 Sept 2025 | - | - | - | Completion Certificate |
|  | Number of multi-Purpose centres constructed | New | 1 multi-Purpose Sports centre constructed at Window level by30 Sept 2025 (Disaneng) | R 5 933 866.16 |  | Site establishment complete and work commenced by 30 Sept 2025 | Installation of parameter fence complete by 31 Dec 2025 | Foundation for superstructure complete by 30 Mar 2026 | 1 multi-Purpose Sports centre constructed at Window level by30 June 2026 | Progress report |
|  | Number of upgraded existing sport complexes installed with artificial turf | New | 1 upgraded existing sport complex by 30 Sept 2025 (Kraaipan) | R 3 525 000.00 |  | Site establishment complete and work commenced by 30 Sept 2025 | Repairs to the parameter fence complete by 31 Dec 2025 | Repairs to existing guardhouse, dressing area and ablution block complete by 30 Mar 2026 | 1 upgraded existing sport complex installed with artificial turf by 30 June 2026 | Progress report |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Good Governance | Number of Audit Charter & Plan developed & reviewed | 1 | Audit Charter & Plan developed by 31 December 2025 | Operational | An Accountable and Transparent Institution | - | 1 Audit Charter & Plan developed by 31 December 2025 | - | - | Council Minutes/ Resolution |
|  | Number of Audit Committee Sittings held | 4 | 4 Audit Committee Sittings held by 30 June 2026 (1 per quarter) | R 200 000 |  | 1 Audit Committee Sittings by 30 September 2025 | 1 Audit Committee Sittings by 31 Dec 2025 | 1 Audit Committee Sittings by 30 March 2026 | 1 Audit Committee Sittings by 30 June 2026 | Minutes & Attendance Registers |
|  | Number of Internal Audits Conducted | 4 Internal Audits | 4 Internal Audits Conducted by 30 June 2026 (1 per quarter) | Operational |  | 1 Internal Audits Conducted by 30 September 2025 | 1 Internal Audits Conducted by 31 Dec 2025 | 1 Internal Audits Conducted by 30 March 2026 | 1 Internal Audits Conducted by 30 June 2026 | Report Signed by the Audit Committee |
|  | Number of Internal Audit (IA) Plan developed & Approved by Audit Committee | 1 | 1 IA Plan developed and approved by Audit Committee by 30 June 2026 | Operational |  | - | - | 1 Draft IA in place by 30 March 2026 | 1 IA Plan developed and approved by Audit Committee by 30 June 2026 | Audit Committee Minutes & Attendance Register |
|  | Number of Risk Management Policies reviewed & adopted | Policy Existing | 1 RMP reviewed & adopted by 30 June 2026 | Operational |  | - | - | 1 Draft RMP in place by 30 March 2026 | 1 RMP reviewed & adopted by 30 June 2026 | Council Minutes, Resolution & RMP |
|  | Number of Internal Audit Reports submitted to Audit Committee for consideration | 4 | 4 Internal Audit Reports submitted to Audit Committee for consideration by 30 June 2026 (1 per quarter) | Operational |  | 1 Internal Audit Reports submitted by 30 September 2025 | 1 Internal Audit Reports submitted by 31 Dec 2025 | 1 Internal Audit Reports submitted by 30 March 2026 | 1 Internal Audit Reports submitted by 30 June 2026 | Minutes, Reports, Attendance Registers & Proof of submission |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Good Governance | Number of revised Risk Management Strategy (RMS) Reviewed and Adopted by Council | Strategy in place | 1 RMS Reviewed and adopted by Council by 31 May 2026 | Operational | An Accountable and Transparent Institution | - | - | 1 Draft Revised RMS in place by 30 March 2026 | 1 RMS Reviewed and adopted by Council by 31 May 2026 | Council Resolution & Adopted RMS |
|  | Number of Revised Fraud and Corruption Strategy adopted by Council | Strategy in place | 1 Revised Fraud & Corruption Strategy Adopted by Council by 31 May 2026 | Operational |  | - | - | 1 Draft Fraud & Corruption Strategy in place by 30 March 2026 | 1 Fraud & Corruption Strategy Revised & adopted by 30 June 2026 | Council Resolution |
|  | Number of MPAC Reports submitted to Council for noting | 4 | 4 MPAC Reports submitted to council for noting by 30 June 2026 (1 per quarter) | R100 000 |  | 1 MPAC Report submitted to council for noting by 30 September 2025 | 1 MPAC Report submitted to council for noting by 31 Dec 2025 | 1 MPAC Report submitted to council for noting by 30 March 2026 | 1 MPAC Report submitted to council for noting by 30 June 2026 | Council Minutes & MPAC Reports |
|  | Number of Ward Committee Functional | 14 | 14 Functional Ward Committees by 30 June 2026 | R2 604 000 | Informed & Involved Community | 14 Functional Ward Committees by 30 September 2025 | 14 Functional Ward Committees by 31 Dec 2025 | 14 Functional Ward Committees by 30 March 2026 | 14 Functional Ward Committees by 30 June 2026 | Ward Committee Minutes, Invite, Agenda & Attendance Register |
|  | Number of Reports submitted to the Office of the Speaker | 4 | 4 Reports on Ward Committees noted by Council by 30 June 2026 | Operational |  | 1 Report on Ward Committees by 30 September 2025 | 1 Report on Ward Committees by 31 Dec 2025 | 1 Report on Ward Committees by 30 March 2026 | 1 Report on Ward Committees by 30 June 2026 | Council Minutes & reports on ward committees |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Revised Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Promote Good Governance | Number of Support Initiatives for Traditional Leaders Implemented | 1 | 4 Support Initiatives for Traditional Leaders Implemented by 30 June 2026 | R 95 000 | informed & Involved Community | 1 Support Initiative by 30 September 2025 | 1 Support Initiative held by 31 December 2025 | 1 Support Initiative held by 30 March 2026 | 1 Support Initiative held by 30 June 2026 | Council Minutes & report on Support Initiatives for Traditional Leaders Implemented |
|  | Number of Communication Strategy Reviewed & Adopted by Council | Strategy in Place | 1 Communication Strategy Reviewed & Adopted by 30 May 2026 | Operational |  | - | - | - | 1 Reviewed & Adopted communication Strategy by 30 May 2026 | Council Resolution & adopted Communication Strategy |
| Promote Community Participation | Number of Youth Summit Held | New | 1 Summit Held by 30 June 2025 | R100 000 | Informed & Involved Community | - | - | - | 1 Summit Held by 30 June 2026 | Minutes & Attendance Registers, & Invite |
|  | Number of Youth Career Exhibition Held | New | 1 YCE Held by 30 June 2026 | R 50 000 |  | - | - | - | 1 YCE Held by 30 June 2026 | Minutes & Attendance Registers & Invite |
|  | Number of Disability Forum Meetings Held | New | 4 Disability Forum Meetings Held by 30 June 2026 (1 per quarter) | R 250 000 |  | 1 Disability Forum Meeting Held by 30 September 2025 | 1 Disability Forum Meeting Held by 31 December 2025 | 1 Disability Forum Meetings Held by 30 March 2026 | 1 Disability Forum Meeting Held by 30 June 2026 | Minutes, Agenda, Attendance register, Invite |
|  | Number of Women’s Forum Meetings Held | 2 | 2 Women’s Forum Meetings Held by 30 June 2026 (1st and 3rd Quarter) | R 100 000 |  | 1 Women’s Forum Meeting Held by 30 September 2025 | - | 1 Women’s Forum Meeting Held by 30 March 2026 | - | Minutes & Attendance Registers, Agenda, Invite |

| KPA: GOOD GOVERNANCE AND PUBLIC PARTICIPATION |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Corporate Objective | Key Performance Indicator | Baseline | Annual Target | Budget | Outcome Indicator | Quarterly Targets |  |  |  | Portfolio of Evidence |
|  |  |  |  |  |  | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4 |  |
| Enhance Communication | Number of Reports on Operational Tele Centres | 1 | 3 Operational Tele Centres by 30 June 2026 (Tshidilamolomo, Kraaipan & Setlagole) | R 300 000 | Informed & Involved Community | 3 Operational Tele Centres by 30 September 2025 (Tshidilamolomo, Kraaipan & Setlagole) | 3 Operational Tele Centres by 31 December 2025 (Tshidilamolomo, Kraaipan & Setlagole) | 3 Operational Tele Centres by 30 March 2026 (Tshidilamolomo, Kraaipan & Setlagole) | 3 Operational Tele Centres by 30 June 2026 (Tshidilamolomo, Kraaipan & Setlagole) | Reports Signed by the MM |
|  | Number of Reports on Moderations & Assessments | 1 | 1 Moderation & Assessment report noted by Council by 30 September 2025 |  |  | 1 Moderation & Assessment report noted by Council by 30 September 2025 | - | - | - | Council Minutes, Moderation & Assessment report |
|  | Number of Certificate Awards Ceremonies held | 1 | 1 Certificate Awards Ceremonies held by 30 September 2025 |  |  | 1 Certificate Award Ceremonies held by 30 September 2025 | - | - | - | Report signed by MM |
|  | Number of Accredited Telecentres | 1 | 1 Telecentre Accredited by 30 September 2025 (Setlagole) |  |  | 1 Telecentre Accredited by 30 September 2025 (Setlagole) | - | - | - | Copy of Accreditation Certificate |
|  | Number of Ratlou Newsletter Publications released | New | 2 Ratlou Newsletter Publications released by 30 June 2026 (Q2 &4) | R 200 000 |  | - | 1 Ratlou Newsletter Publications released by 31 December 2025 | - | 1 Ratlou Newsletter Publications released by 30 June 2026 | Copies of the Newsletter |

CHAPTER 4

# MUNICIPAL FINANCIAL INFORMATION

This section contains the financial information of the municipality as contained in the 2025/2026 municipal budget.

The first part of the section consists of the municipality’s projected income by source. This represents all the income that the municipality will receive for the 2025/2026 financial year.

This section is followed by the projected expenditure of council by vote. Here the municipality indicates present its expenditure plan in line with its projected income.

The last part of this section consists of the ward information where the location of each project will be based in the municipal area.  Readers and residents alike should be able to use the information in this section to see the distribution of projects in the municipal area and the most importantly to follow the development trends.

# COMPONENT 1: MONTHLY PROJECTIONS OF REVENUE TO BE COLLECTED FOR EACH SOURCE

| NW381 Ratlou - Supporting Table SA25 Budgeted monthly revenue and expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | Budget Year 2025/26 |  |  |  |  |  |  |  |  |  |  |  | Medium Term Revenue and Expenditure Framework |  |  |
| R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2025/26 | Budget Year +1 2026/27 | Budget Year +2 2027/28 |
| Revenue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Exchange Revenue |  | 20% | 5% | 5% | 5% | 20% | 5% | 5% | 5% | 20% | 3% | 3% |  |  |  |  |
| Service charges - Electricity |  | 136 | 34 | 34 | 34 | 136 | 34 | 34 | 34 | 136 | 20 | 20 | 27 | 680 | 708 | 736 |
| Service charges - Water |  | – | – | – | – | – | – | – | – | – | – | – | – | – | 0 | 0 |
| Service charges - Waste Water Management |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Service charges - Waste Management |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Sale of Goods and Rendering of Services |  | 73 | 18 | 18 | 18 | 73 | 18 | 18 | 18 | 73 | 11 | 11 | 15 | 365 | 744 | 714 |
| Agency services |  | 222 | 56 | 56 | 56 | 222 | 56 | 56 | 56 | 222 | 33 | 33 | 44 | 1 112 | 1 202 | 1 156 |
| Interest |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Interest earned from Receivables |  | 681 | 170 | 170 | 170 | 681 | 170 | 170 | 170 | 681 | 102 | 102 | 136 | 3 405 | 0 | 0 |
| Interest earned from Current and Non Current Assets |  | 1 242 | 310 | 310 | 310 | 1 242 | 310 | 310 | 310 | 1 242 | 186 | 186 | 248 | 6 210 | 6 717 | 6 458 |
| Dividends |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Rent on Land |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Rental from Fixed Assets |  | 433 | 108 | 108 | 108 | 433 | 108 | 108 | 108 | 433 | 65 | 65 | 87 | 2 163 | 2 339 | 2 249 |
| Licence and permits |  | 40 | 10 | 10 | 10 | 40 | 10 | 10 | 10 | 40 | 6 | 6 | 8 | 202 | 219 | 210 |
| Operational Revenue |  | 28 | 7 | 7 | 7 | 28 | 7 | 7 | 7 | 28 | 4 | 4 | 6 | 140 | 3 702 | 3 561 |
| Non-Exchange Revenue |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Property rates |  | 5 907 | 1 477 | 1 477 | 1 477 | 5 907 | 1 477 | 1 477 | 1 477 | 5 907 | 886 | 886 | 1 181 | 29 536 | 30 717 | 31 946 |
| Surcharges and Taxes |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Fines, penalties and forfeits |  | 35 | 9 | 9 | 9 | 35 | 9 | 9 | 9 | 35 | 5 | 5 | 7 | 176 | 190 | 183 |
| Licences or permits |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Transfer and subsidies - Operational |  | 35 281 | 8 820 | 8 820 | 8 820 | 35 281 | 8 820 | 8 820 | 8 820 | 35 281 | 5 292 | 5 292 | 7 056 | 176 403 | 182 744 | 177 623 |
| Interest |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Fuel Levy |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Operational Revenue |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Gains on disposal of Assets |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Other Gains |  | – | 0 | 0 | – | – | – | – | – | – | – | – | (0) | – | 0 | 0 |
| Discontinued Operations |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Total Revenue (excluding capital transfers and contributions) |  | 44 078 | 11 020 | 11 020 | 11 020 | 44 078 | 11 020 | 11 020 | 11 020 | 44 078 | 6 612 | 6 612 | 8 816 | 220 390 | 229 283 | 224 836 |
| Expenditure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employee related costs |  | 22 566 | 5 642 | 5 642 | 5 642 | 22 566 | 5 642 | 5 642 | 5 642 | 22 566 | 3 385 | 3 385 | 4 513 | 112 832 | 113 760 | 118 294 |
| Remuneration of councillors |  | 2 791 | 698 | 698 | 698 | 2 791 | 698 | 698 | 698 | 2 791 | 419 | 419 | 558 | 13 955 | 14 513 | 15 094 |
| Bulk purchases - electricity |  | 968 | 242 | 242 | 242 | 968 | 242 | 242 | 242 | 968 | 145 | 145 | 194 | 4 840 | 5 762 | 5 992 |
| Inventory consumed |  | 424 | 106 | 106 | 106 | 424 | 106 | 106 | 106 | 424 | 64 | 64 | 85 | 2 120 | 2 133 | 2 248 |
| Debt impairment |  | 1 400 | 350 | 350 | 350 | 1 400 | 350 | 350 | 350 | 1 400 | 210 | 210 | 280 | 7 000 | 7 280 | 7 571 |
| Depreciation and amortisation |  | 6 608 | 1 652 | 1 652 | 1 652 | 6 608 | 1 652 | 1 652 | 1 652 | 6 608 | 991 | 991 | 1 322 | 33 041 | 37 586 | 38 330 |
| Interest |  | 12 | 3 | 3 | 3 | 12 | 3 | 3 | 3 | 12 | 2 | 2 | 2 | 60 | 62 | 65 |
| Contracted services |  | 7 294 | 1 824 | 1 824 | 1 824 | 7 294 | 1 824 | 1 824 | 1 824 | 7 294 | 1 094 | 1 094 | 1 459 | 36 470 | 34 691 | 36 083 |
| Transfers and subsidies |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Irrecoverable debts written off |  | 196 | 49 | 49 | 49 | 196 | 49 | 49 | 49 | 196 | 29 | 29 | 39 | 980 | 1 019 | 1 060 |
| Operational costs |  | 9 132 | 2 283 | 2 283 | 2 283 | 9 132 | 2 283 | 2 283 | 2 283 | 9 132 | 1 370 | 1 370 | 1 826 | 45 659 | 57 045 | 69 792 |
| Losses on disposal of Assets |  | – | – | – | – | – | – | – | – | – | – | – | – | – | – | – |
| Other Losses |  | 8 | 2 | 2 | 2 | 8 | 2 | 2 | 2 | 8 | 1 | 1 | 2 | 40 | 42 | 43 |
| Total Expenditure |  | 51 399 | 12 850 | 12 850 | 12 850 | 51 399 | 12 850 | 12 850 | 12 850 | 51 399 | 7 710 | 7 710 | 10 280 | 256 997 | 273 894 | 294 573 |
| Surplus/(Deficit) |  | (7 321) | (1 830) | (1 830) | (1 830) | (7 321) | (1 830) | (1 830) | (1 830) | (7 321) | (1 098) | (1 098) | (1 464) | (36 606) | (44 611) | (69 737) |
| Transfers and subsidies - capital (monetary allocations) |  | 6 781 | 1 695 | 1 695 | 1 695 | 6 781 | 1 695 | 1 695 | 1 695 | 6 781 | 1 017 | 1 017 | 1 356 | 33 906 | 35 263 | 36 673 |
| Transfers and subsidies - capital (in-kind) |  | – |  |  |  |  |  |  |  |  |  |  | – | – | – | – |
| Surplus/(Deficit) after capital transfers & contributions |  | (540) | (135) | (135) | (135) | (540) | (135) | (135) | (135) | (540) | (81) | (81) | (108) | (2 700) | (9 349) | (33 063) |
| Income Tax |  |  |  |  |  |  |  |  |  |  |  |  | – | – | – | – |
| Surplus/(Deficit) after income tax |  | (540) | (135) | (135) | (135) | (540) | (135) | (135) | (135) | (540) | (81) | (81) | (108) | (2 700) | (9 349) | (33 063) |
| Share of Surplus/Deficit attributable to Joint Venture |  |  |  |  |  |  |  |  |  |  |  |  | – | – | – | – |
| Share of Surplus/Deficit attributable to Minorities |  |  |  |  |  |  |  |  |  |  |  |  | – | – | – | – |
| Surplus/(Deficit) attributable to municipality |  | (540) | (135) | (135) | (135) | (540) | (135) | (135) | (135) | (540) | (81) | (81) | (108) | (2 700) | (9 349) | (33 063) |
| Share of Surplus/Deficit attributable to Associate |  |  |  |  |  |  |  |  |  |  |  |  | – | – | – | – |
| Intercompany/Parent subsidiary transactions |  |  |  |  |  |  |  |  |  |  |  |  | – | – | – | – |
| Surplus/(Deficit) for the year | 1 | (540) | (135) | (135) | (135) | (540) | (135) | (135) | (135) | (540) | (81) | (81) | (108) | (2 700) | (9 349) | (33 063) |

COMPONENT 2: MONTHLY PROJECTIONS OF EXPENDITURE (OPERATING & CAPITAL) AND REVENUE FOR EACH VOTE

| NW381 Ratlou - Supporting Table SA26 Budgeted monthly revenue and expenditure (municipal vote) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | Budget Year 2025/26 |  |  |  |  |  |  |  |  |  |  |  | Medium Term Revenue and Expenditure Framework |  |  |
| R thousand |  | July | August | Sept. | October | November | December | January | February | March | April | May | June | Budget Year 2025/26 | Budget Year +1 2026/27 | Budget Year +2 2027/28 |
| Revenue by Vote |  | 20% | 5% | 5% | 5% | 20% | 5% | 5% | 5% | 20% | 3% | 3% |  |  |  |  |
| Vote 1 - Executive and Council |  | 5 550 | 1 387 | 1 387 | 1 387 | 5 550 | 1 387 | 1 387 | 1 387 | 5 550 | 832 | 832 | 1 110 | 27 748 | 28 858 | 30 012 |
| Vote 2 - Finance and Administration |  | 13 964 | 3 491 | 3 491 | 3 491 | 13 964 | 3 491 | 3 491 | 3 491 | 13 964 | 2 095 | 2 095 | 2 793 | 69 821 | 72 614 | 75 519 |
| Vote 3 - Public Safety |  | 6 851 | 1 713 | 1 713 | 1 713 | 6 851 | 1 713 | 1 713 | 1 713 | 6 851 | 1 028 | 1 028 | 1 370 | 34 256 | 35 626 | 37 051 |
| Vote 4 - Planning and Development |  | 17 820 | 4 455 | 4 455 | 4 455 | 17 820 | 4 455 | 4 455 | 4 455 | 17 820 | 2 673 | 2 673 | 3 564 | 89 100 | 92 664 | 96 371 |
| Total Revenue by Vote |  | 44 185 | 11 046 | 11 046 | 11 046 | 44 185 | 11 046 | 11 046 | 11 046 | 44 185 | 6 628 | 6 628 | 8 837 | 220 925 | 229 762 | 238 953 |
| Expenditure by Vote to be appropriated |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Vote 1 - Executive and Council |  | 8 712 | 2 178 | 2 178 | 2 178 | 8 712 | 2 178 | 2 178 | 2 178 | 8 712 | 1 307 | 1 307 | 1 742 | 43 560 | 45 303 | 47 115 |
| Vote 2 - Finance and Administration |  | 20 507 | 5 127 | 5 127 | 5 127 | 20 507 | 5 127 | 5 127 | 5 127 | 20 507 | 3 076 | 3 076 | 4 101 | 102 534 | 106 635 | 110 900 |
| Vote 3 - Public Safety |  | 7 728 | 1 932 | 1 932 | 1 932 | 7 728 | 1 932 | 1 932 | 1 932 | 7 728 | 1 159 | 1 159 | 1 546 | 38 640 | 40 186 | 41 793 |
| Vote 4 - Planning and Development |  | 13 485 | 3 371 | 3 371 | 3 371 | 13 485 | 3 371 | 3 371 | 3 371 | 13 485 | 2 023 | 2 023 | 2 697 | 67 423 | 70 120 | 72 924 |
| Vote 5 - Energy Sources |  | 968 | 242 | 242 | 242 | 968 | 242 | 242 | 242 | 968 | 145 | 145 | 194 | 4 840 | 5 762 | 5 992 |
| Total Expenditure by Vote |  | 51 399 | 12 850 | 12 850 | 12 850 | 51 399 | 12 850 | 12 850 | 12 850 | 51 399 | 7 710 | 7 710 | 10 280 | 256 997 | 268 005 | 278 725 |
| Surplus/(Deficit) before assoc. |  | (7 214) | (1 804) | (1 804) | (1 804) | (7 214) | (1 804) | (1 804) | (1 804) | (7 214) | (1 082) | (1 082) | (1 443) | (36 071) | (38 242) | (39 772) |
| Surplus/(Deficit) | 1 | (7 214) | (1 804) | (1 804) | (1 804) | (7 214) | (1 804) | (1 804) | (1 804) | (7 214) | (1 082) | (1 082) | (1 443) | (36 071) | (38 242) | (39 772) |

# Capital and Special Projects Monthly Projections

| PROJECT | BUDGET 2025/2026 | Monthly Projections (R) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | July 2025 | Aug 2025 | Sept 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | June 2026 |
| Supply, delivery and installation of High Mast Lights in Ward 06 | R 3 213 151 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 | 267 762.58 |
| Construction of 2.5 km internal access roads in Makgobistad - Completion | R 5 768 750 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 | 480 729.16 |
| Supply, delivery and installation of concrete palisade fence and 6 VIP toilets at Ward 05 | R 467 612.65 | 155 870.88 | 155 870.88 | 155 870.88 |  |  |  |  |  |  |  |  |  |
| Construction of 2.5 km internal access road in Setlhwatlhwe – Ward 13 | R 5 002 937.37 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 | 416 911 44 |
| Construction of Gareleng Community Hall – Completion of works | R 954 833.64 | 318 277.88 | 318 277.88 | 318 277.88 |  |  |  |  |  |  |  |  |  |
| Construction of 2.5km internal access roads in ward 08 - Kraaipan | R3 678 918,92 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 | 306 576.57 |
| Upgrading of an existing Sports Complex in Ward 11 | R3 525 000,00 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 | 293 750 |
| Construction of a 3.5km internal access road in Ward 14 | R5 361 380,30 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 | 446 781.69 |
| Construction of Disaneng Multi-Sports Centre | R 5 933 866,16 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 | 494 488.84 |
| Construction of Drivers Licence Testing grounds | R 3 000 000.00 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 | 250 000 |
| PMU Administration | R 1 784 550.00 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 | 148 712.50 |
| Total (R) | R 36 700 000.04 | 3579861.54 | 3579861.54 | 3579861.54 | 2939046.11 | 3105712.78 | 3105712.78 | 3105712.78 | 3105712.78 | 3105712.78 | 3105712.78 | 3105712.78 | 3105712.78 |

# Capital Projects Three Year Plan

| PROJECT | 2025/2026 | 2026/2027 | 2027/2028 |
| --- | --- | --- | --- |
| Supply, delivery and installation of High Mast Lights in Ward 06 | R 3 213 151 | R 5,000,000.00 | R 2,000,000.00 |
| Construction of 2.5 km internal access roads in Makgobistad - Completion | R 5 768 750 | R 9 843 650.19 | R 1 775 000.00 |
| Supply, delivery and installation of concrete palisade fence and 6 VIP toilets at Ward 05 | R 467 612.65 | R 2,000,000.00 | R 500,000.00 |
| Construction of 2.5 km internal access road in Setlhwatlhwe – Ward 13 | R 5 002 937.37 | R 3 087 086.37 | R 3 000 000 |
| Construction of Gareleng Community Hall – Completion of works | R 954 833.64 | R 400 000.00 | R - |
| Construction of 2.5km internal access roads in ward 08 - Kraaipan | R3 678 918,92 | R 1 500 000.00 | R 2 456 250.00 |
| Upgrading of an existing Sports Complex in Ward 11 | R3 525 000,00 | R 3 225 000.00 | R 2,000,000.00 |
| Construction of a 3.5km internal access road in Ward 14 | R5 361 380,30 | R 3 389 075.00 | R 4 087 500.00 |
| Construction of Disaneng Multi-Sports Centre | R 5 933 866,16 | R 3 749 999.99 | R 2 690 079.92 |
| Construction of Drivers Licence Testing grounds | R 1 000 000.00 |  |  |
| Upgrading of an existing Sports Complex in Ward 10 - Phase 02 | R - | R 1 750 000,00 | R 2 724 658,08 |
| Supply, delivery and installation of five (5) high-mast lights in ward 04 | R - | R 2 750 000,00 |  |
| Upgrading of 2.5km internal access road in ward 09 | R - | R - | R 17 750 000,00 |
| Supply, delivery and installation of 8 High-mast lights in ward 05 | R - | R 4 606 425,63 | - |
| Supply, delivery and installation of 5 High-mast lights in ward 01 | R - | R2 303 212,82 | R - |
| Supply, delivery and installation of 10 High-mast lights in ward 02 | R - | R - | R 3 684 662,00 |
| PMU Administration | R 1 784 550,00 | R 1 926 550,00 | R 2 008 850,00 |
| TOTALS | R 36 691 004.04 | R 38,531,000.00 | R 40,177, 000.00 |

| INFRASTRUCTURE PROJECTS | WARD | 2022/2023 |
| --- | --- | --- |
| Supply, delivery and installation of High Mast Lights | 06 | R 3 213 151 |
| Construction of 2.5 km internal access roads in Makgobistad - Completion | 02 | R 5 768 750 |
| Supply, delivery and installation of concrete palisade fence and 6 VIP toilets | 05 | R 467 612.65 |
| Construction of 2.5 km internal access road in Setlhwatlhwe | 13 | R 5 002 937.37 |
| Construction of Gareleng Community Hall – Completion of works | 09 | R 954 833.64 |
| Construction of 2.5km internal access roads in ward | 08 | R3 678 918,92 |
| Upgrading of an existing Sports Complex | 11 | R3 525 000,00 |
| Construction of a 3.5km internal access road | 14 | R5 361 380,30 |
| Construction of Disaneng Multi-Sports Centre | 03 | R 5 933 866,16 |
| Construction of Drivers Licence Testing grounds | 14 | R 1 000 000.00 |
| PMU Administration |  | R 1 784 550,00 |
| Total |  | R 36 691 000.04 |

4.3 WARD INFORMATION

4.4 Maintenance Projects (Infrastructure)

| INFRASTRUCTURE PROJECTS | 2025/2026 | 2026/2027 | 2027/2028 |
| --- | --- | --- | --- |
| Materials-Tools | 500 000 | 520 000 | 540 800 |
| High Mast Lights/Flood light-maintenance | 2 500 000 | 2 600 000 | 2 704 000 |
| Sceptic Tanks | 200,000 | 212,000 | 224,720 |
| Facilities Maintenance | 7 000 000 | 3 120 000 | 3 244 800 |
| Stand -by Generator | 80,000 | 84,800 | 89,888 |
| Maintenance of Plant Machinery | 200 000 | 208 000 | 216 320 |
| TOTAL | 6 530 000 | 6 796 800 | 7 074 608 |